DRAFT - 2024 ACTION PLAN

FOR IMPLEMENTATION OF THE

PFM REFORM PROGRAMME

March 2024

| PILLAR: I - Economic Analysis, Macroeconomic and Fiscal Framework |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PRIORITY 1: Revenue forecasting and reporting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Priority outcomes | Priority indicators |  |  |  | Target FY 2024 |  |  | Target FY 2025 |  |  | Target FY 2026 |  |  |  |  | Target FY 2027 |  |  |
| i) The Aggregate revenue deviation and variance in revenue composition between planned and actual figures is reduced, indicating in particular improved forecasting of income and profit tax, VAT and excise and social security contributions | Aggregate revenue deviation and variance in revenue composition between planned and actual figures (as used in PEFA PI3) |  |  |  | Score B |  |  | Score B |  |  | Score A |  |  |  |  | Score A |  |  |
| ii) Enhanced public awareness of the size and scope of tax expenditures and other tax indicators | Tax expenditures reports are prepared and published as part of the Final Account of the State Budget |  |  |  | Annual Tax Expenditure Report prepared; Realized trainings for оther tax reports (VAT-GAP; C-efficiency; Tax buoyancy and tax elasticity) |  |  | Annual Tax Expenditure Report prepared and published as part of the Final Account of the State Budget; Other tax reports prepared (VAT-GAP Report, Coefficients for tax buoyancy and tax elasticity and C-Efficiency) ; Realized trainings for preparation of report on estimated еffective marginal tax rates (EMTRs) and effective average tax rates (EATRs);) |  |  | Annual Tax Expenditure Report prepared and published as part of the Final Account of the State Budget. Other tax reports prepared (VAT-GAP Report, Coefficients for tax buoyancy and tax elasticity, C-Efficiency and Effective marginal tax rates (EMTRs) and effective average tax rates (EATRs) Report). Realized trainings for preparation of report on Income inequality and Cost-of-collection ratio. |  |  |  |  | Annual Tax Expenditure Report prepared and published as part of the Final Account of the State Budget; Other tax reports prepared (VAT-GAP Report, Coefficients for tax buoyancy and tax elasticity, Income inequality report, C-Efficiency, Cost-of-collection ratio Report, and Effective marginal tax rates (EMTRs) and effective average tax rates (EATRs) Report) |  |  |
| iii) Enhaced modeling capabilities of the MoF staff and advanced revenue monitoring and analysis | Staff is fully trained for applying the tax models for revenue forecasting, monitoring and analysis of any deviations in tax revenue mobilization and for estimating tax expenditures |  |  |  | 8 staff training performed |  |  | Regular annual staff training in tax modeling |  |  | Regular annual staff training in tax modeling |  |  |  |  | Regular annual staff training in tax modeling |  |  |
| MEASURE 1: Improving tax and customs reporting in accordance with the EU best practices |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: |  |  | Measure indicator: |  |  | Target FY 2024 |  |  | Target FY 2025 |  |  | Target FY 2026 |  |  |  |  | Target FY 2027 |  |
| The objective is to improve tax and customs reporting in line with the EU practices, as well as other standards (e.g. IMF Fiscal Transparency code), as well as enhance the transparency of the tax system and tax instruments. |  |  | Number of data sharing protocols signed and implemented |  |  | Data sharing protocols signed with the PRO, CA, SSO, MLSP, MOE, CR |  |  | Data protocols signed with all other relevant institutions |  |  | Continuous update of signed data sharing protocols |  |  |  |  | Continuous update of signed data sharing protocols |  |
|  |  |  | Number of published reports per year and realized trainings for preparation of the reports |  |  | Annual tax expenditure prepared; Realized trainings for оther tax reports (VAT-GAP; C-efficiency; Tax buoyancy and tax elasticity) |  |  | Annual tax expenditures report prepared and published as part of the Final Account of the State Budget; Other tax reports prepared (VAT-GAP Report, Coefficients for tax buoyancy and tax elasticity and C-Efficiency) ; Realized trainings for preparation of report on estimated еffective marginal tax rates (EMTRs) and effective average tax rates (EATRs);) |  |  | Annual tax expenditures report prepared and published as part of the Final Account of the State Budget. Other tax reports prepared (VAT-GAP Report, Coefficients for tax buoyancy and tax elasticity, C-Efficiency and Effective marginal tax rates (EMTRs) and effective average tax rates (EATRs) Report). Realized trainings for preparation of report on Income inequality and Cost-of-collection ratio. |  |  |  |  | Annual tax expenditures report prepared and published as part of the Final Account of the State Budget; Other tax reports prepared (VAT-GAP Report, Coefficients for tax buoyancy and tax elasticity, Income inequality report, C-Efficiency, Cost-of-collection ratio Report, and Effective marginal tax rates (EMTRs) and effective average tax rates (EATRs) Report) |  |
| Deliverables in 2024: |  | Trainings of the employees of the Tax Analysis Unit at the Ministry of Finance on tax reporting and preparation of a tax expenditure report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  |  |  |  | PLANNED INPUTS |  |  |  |
|  |  |  |  | START qq/yy |  | END qq/yy |  |  |  |  |  |  |  | BUDGET |  |  |  | SOURCE |
| 1. Establish an effective and efficient tax data sharing mechanism |  |  |  | Q1/24 |  | Q4/24 | MoF |  |  | PRO and CA |  |  |  | EUR 90,000 for 2024 (budgeted ammount for both activity 1&2) |  |  |  | IMF |
| 2. Preparation of Tax expenditures report and other tax reports in line with EU best practices |  |  |  | Q1/24 |  | Q4/24 | MoF |  |  | PRO and CA |  |  |  |  |  |  |  | IMF |
| MEASURE 2: Enhancing tax and customs modelling capacity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: |  |  | Measure indicator: |  |  | Target FY 2024 |  |  | Target FY 2025 |  |  | Target FY 2026 |  |  |  |  | Target FY 2027 |  |
| Enhance tax and customs modelling capacity of the Ministry of Finance by using tax models and data-science tools. |  |  | Number of provided tailor-made training of staff |  |  | Implemented 1 training in cost-benefit analysis of tax expenditures; Implemented 6 trainings for tax modeling Implemented 1 training for Power BI |  |  | Implemented regular annual staff training in tax modeling |  |  | Implemented regular annual staff training in tax modeling |  |  |  |  | Implemented regular annual staff training in tax modeling |  |
|  |  |  | Number of tax models fully operational; new modules for tax expenditures developed and Power BI tool installed |  |  | 3 tax models fully implemented, with 4 extensions with a module for tax expenditures; Power BI tool installed |  |  | 4 tax models fully implemented, with 4 extensions with a module for tax expenditures, Power BI tool installed |  |  | 4 tax models fully implemented, with 4 extensions with a module for tax expenditures; Power BI tool installed. Staff is trained in using the models |  |  |  |  | 4 tax models fully implemented, with 4 extensions with a module for tax expenditures; Power BI tool installed. Staff is fully trained in using the models |  |
| Deliverables in 2024: |  | Trainings of the employees of the Tax Analysis Unit at the Ministry of Finance on tax modelling |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  |  |  |  | PLANNED INPUTS |  |  |  |
|  |  |  |  | START qq/yy |  | END qq/yy |  |  |  |  |  |  |  | BUDGET |  |  |  | SOURCE |
| 1. Implementation of developed tax models and further training of staff |  |  |  | Q1/24 |  | Q1/24 | MoF |  |  | PRO and CA |  |  |  | EUR 110,000 for 2024 (budgeted ammount for both activity 1&2) |  |  |  | WB |
| 2. Extending the tax models with new modules and installation of Power BI tool. |  |  |  | Q1/24 |  | Q1/24 | MoF |  |  | PRO and CA |  |  |  |  |  |  |  | WB |
|  |  |  |  |  |  |  |  |  |  |  |  |  | TOTAL: |  |  |  |  | EUR 200,000 |

| PILLAR I: Economic Analysis, Macroeconomic and Fiscal Framework |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PRIORITY 2: Economic analysis and Macroeconomic forecasting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Priority outcomes | Priority indicators | Target FY 2024 |  |  |  |  | Target FY 2025 |  |  | Target FY 2026 |  |  |  | Target FY 2027 |  |
| Impact assessment of certain economic policies, reforms or measures and carrying out of additional economic analyses | •Deviation between realised and forecasted GDP •Deviation between actual and budgeted expenditures for specified risk-prone expenditures | Conducted trainings and workshops on the assessment of the impact of structural policies using existing and new tools |  |  |  |  | Conducted trainings and workshops on the assessment of the impact of structural policies using existing and new tools |  |  | Increased scope of economic analyses and impact assessments of labour market, informal economy, economy's productivity and competitiveness, etc |  |  |  |  |  |
| Improved quality and coverage of projections for macroeconomic indicators |  | Development of new tools for macroeconomic planning and forecasting as well as policy analyses: - GDP short-term model to be upgraded - Macro –fiscal structural model to be developed - Conducted trainings, incl. on econometrics |  |  |  |  | Development of new tools for macroeconomic planning and forecasting as well as policy analyses: - GDP short-term model to be upgraded - Macro –fiscal structural model to be developed - Conducted trainings, incl. on econometrics |  |  | New tools (short term and macro –fiscal structural models) for forecasting and analyses to be completed. Conducted trainings and workshops on the use of models |  |  |  | Action plan for development of a CGE model completed |  |
| Increased scope of fiscal risks assessment and analyses (for all types of fiscal risks determined in line with the good international practices) |  | - Initial activities for strengthening institutional framework for fiscal risks - Assessment of current state of play in relation to fiscal risks and draft plan for follow up short and medium term activities |  |  |  |  | Procedure for comprehensive Fiscal Risks Statement as part of the draft Budget |  |  | Updated plan of activities for strengthening capacities for fiscal risks assessment and analyses |  |  |  |  |  |
| Independent, objective and professional opinions on issues related to fiscal policy |  | - Establishing data sharing arrangements for the needs of the Fiscal Council - Building capacity at the administrative and technical bodies of the Fiscal Council |  |  |  |  | - Building capacity at the administrative and technical bodies of the Fiscal Council |  |  | Updated plan of activities for operation of the Fiscal Council |  |  |  |  |  |
| MEASURE 1: Capacity building for economic analyses |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  | Target FY 2024 |  |  | Target FY 2025 |  |  | Target FY 2026 |  | Target FY 2027 |  |  |
| To strengthen the capacities of the beneficiaries for economic analyses in order to provide policy makers information on the expected results of the proposed economic measures, including through introduction of additional macro fiscal toolkits. | Assessment of the impact of certain economic policies, reforms or measures and implementation of additional economic analyses. |  |  |  | Conducted trainings and workshops on the assessment of the impact of structural policies using existing and new tools. |  |  | Conducted trainings and workshops on the assessment of the impact of structural policies using existing and new tools. |  |  | Increased scope of economic analyses and impact assessments of labour market, informal economy, economy's productivity and competitiveness, etc. |  |  |  |  |
| Deliverables in 2024: | Trainings of employees in the Ministry of Finance for the analysis of macroeconomic data Developing a tool model for assessing the impact of economic policies and reforms with a financial programming model |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  |  | PLANNED INPUTS |  |  |  |
|  |  |  | START qq/yy | END qq/yy |  |  |  |  |  |  |  | BUDGET |  |  | SOURCE |
| 1. Increasing the scope of economic analyses. Continuation of the development of a new tool to improve analyses of the economic trends including: labor market developments, the informal economy, the assessment of the productivity and the competitiveness of the economy, etc. |  |  | Q1/24 | Q2/26 |  | MоF (DEPD, DT, DBF, DPD) |  |  |  |  |  | EUR 70,000 for 2024 |  |  | External financing Swiss State Secretariat for Economic Affairs (SECO) |
| 2. Economic policy impact assessment. Continuation of the development of a new tool to improve assessment of the impact from certain economic policies, reforms or measures. |  |  | Q1/24 | Q3/26 |  | MоF (DEPD, DT, DBF, DPD) |  |  |  |  |  |  |  |  |  |
| MEASURE 2: Developing new macroeconomic models |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  | Target FY 2024 |  |  | Target FY 2025 |  |  | Target FY 2025 |  | Target FY 2026 |  |  |
| Strengthening the capacity of the Ministry of Finance for macroeconomic forecasting and analyses, including by development of new econometric models. | New macroeconomic models in the preparation of budget documents and the Program for Economic Reforms |  |  |  | Development of new tools for macroeconomic analyses and forecasting: - To upgrade GDP short-term model - To start developing Macro – fiscal structural model - Conduct trainings on econometrics |  |  | Development of new tools for macroeconomic analyses and forecasting: - Macro –fiscal structural model to be further developed - Conduct trainings on econometrics |  |  | New tools (short term and macro –fiscal structural models) for forecasting and analyses to be completed. Conducted trainings and workshops on the use of models Action plan for development of a CGE model completed |  |  |  |  |
| Deliverables in 2024: | New macroeconomic models in the preparation of budget documents and the Program for Economic Reforms - GDP short-term model to be upgraded - Start development of Macro –fiscal structural model - Conducted trainings, incl. on econometrics |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  |  | PLANNED INPUTS |  |  |  |
|  |  |  | START qq/yy | END qq/yy |  |  |  |  |  |  |  | BUDGET |  |  | SOURCE |
| Developing macroeconomic forecasting tools: - Macro –fiscal structural model to be developed - GDP short-term model to be upgraded - Conducting trainings in the field of econometrics |  |  | Q1/24 | Q4/26 |  | MоF (DEPD for line 1&2), MoF (DEPD, DBF, DT, DPD -line 3), |  |  | Parliament-BO &PI); F.Council, Academia(line 3) |  |  | Eur 70,000 for 2024 |  |  | Eur 7.100.000 m.e. for World Bank project ‘Strengthening fiscal governance in the Western Balkans 2023-26’ (World Bank) under the EU TF on strengthening the fiscal governance in the Western Balkans. |
| MEASURE 3: Fiscal Risks |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  | Target FY 2024 |  |  | Target FY 2025 |  |  | Target FY 2026 |  | Target FY 2027 |  |  |
| To strengthen the institutional architecture of beneficiaries for fiscal risks assessment in order to provide timely information on potential threats to the country's fiscal position and an integrated approach to managing these risks. | Comprehensive reporting (Fiscal Risks Statement) on: liabilities of central and local governments; PPP associated risks; summary of risks identified by the biggest SoEs; comparison of macro-fiscal forecast scenarios |  |  |  | - Assessment of current state of play in relation to fiscal risks and draft plan for follow up short and medium term activities - Fiscal risk working group established - Institutional responsibilities clarified; - First enhancements to fiscal risk chapter in Fiscal Strategy |  |  | - Complete procedures for comprehensive Fiscal Risks Statement - Analysis of fiscal risks from SOEs, PPPs, legal claims. |  |  | Plan for further development of fiscal risks assessment and analyses (2026) |  |  |  |  |
| Deliverables in 2024: | Trainings of employees in the Ministry of Finance for fiscal risks analysis |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  |  | PLANNED INPUTS |  |  |  |
|  |  |  | START qq/yy | END qq/yy |  |  |  |  |  |  |  | BUDGET |  |  | SOURCE |
| 1. Establishing institutional framework for fiscal analyses at MoF and assessment of current reporting of fiscal risks with recommendations for improvement in the short and medium term |  |  | Q1/24 | Q4/26 |  | MoF (DEPD, DBF, DT, DPD, LD) |  |  |  |  |  | Eur 100,000 for 2024 |  |  | IMF missions on Fiscal Risks/EU/SECO |
| 2. Preparing consolidated Fiscal Risk Statement, as part of the draft Budget |  |  | Q3/24 | Q3/24 |  | MoF (DEPD, DBF, DT, DPD, LD) |  |  |  |  |  |  |  |  |  |
| MEASURE 4: Fiscal Council Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  | Target FY 2024 |  |  | Target FY 2025 |  |  | Target FY 2026 |  | Target FY 2027 |  |  |
| To improve assessments of fiscal policies and strengthen fiscal policy credibility in terms of compliance with the set fiscal rules stated in the Organic Budget Law, thus strengthening transparency and the accountability | Operational Fiscal Council and a body for professional administrative support |  |  |  | Established body for administrative-technical support of Fiscal Council Prepared data sharing agreements between FC, MoF and other institutions |  |  | Fiscal Council publishes its independent report on macro-fiscal sustainability |  |  | Plan for further strengthening of the capacities of the Fiscal Council independence, objectivity and quality of professional opinions on issues related to fiscal policies |  |  |  |  |
| Deliverables in 2024: | Trainings of employees in the Fiscal Council and Ministry of Finance and signing memorandums of understandings for data exchange between the Fiscal Council and relevant institutions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  |  | PLANNED INPUTS |  |  |  |
|  |  |  | START qq/yy | END qq/yy |  |  |  |  |  |  |  | BUDGET |  |  | SOURCE |
| 1. Putting in place an effective data sharing arrangements for the needs of the Fiscal Councils |  |  | Q2/24 | Q4/25 |  | Fiscal Council, MoF |  |  |  |  |  | Eur 100,000 for 2024 |  |  | 7.1 m.e. for World Bank project ‘Strengthening fiscal governance in the Western Balkans 2023-26’ (World Bank) under the EU TF on strengthening the fiscal governance in the Western Balkans. |
| 2. Building administrative capacity |  |  | Q3/24 | Q4/26 |  | Fiscal Council, MoF |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | TOTAL: |  |  | EUR 340,000 |

| PILLAR 1: Economic Analysis, Macroeconomic and Fiscal Framework |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PRIORITY 3: Strengthening Debt management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Priority outcomes | Priority indicators | Target FY 2024 |  |  |  |  | Target FY 2025 |  |  | Target FY 2026 |  |  | Target FY 2027 |  |
| Strengthened public debt management | Increased grade for the indicator 6.4.1 - Quality of public debt management in SIGMA report. | / |  |  |  |  | / |  |  | / |  |  | Improvement of the indicator in the SIGMA report for risk mitigation in the stock of public debt |  |
| MEASURE 1: Reducing operational risks at public debt management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  | Target FY 2024 |  |  | Target FY 2025 |  |  | Target FY 2026 |  |  | Target FY 2027 |
| More efficient public debt management by optimizing risks which public debt portfolio is susceptible to. | Number of external debt orders paid electronically |  |  |  | 80% of external debt orders to be realized electronically |  |  | 100% of external debt orders to be realized electronically |  |  | / |  |  | / |
|  | Increased number of employees responsible for public debt management |  |  |  | 16 employees for public debt management |  |  | 17 employees for public debt management |  |  | 18 employees for public debt management |  |  | 19 employees for public debt management |
|  | Procedure for Quarterly debt reconciliation with foreign creditors |  |  |  | Adopted procedure for Quarterly debt reconciliation with foreign creditors |  |  | / |  |  | Adopted procedure for Quarterly debt reconciliation with foreign creditors |  |  | / |
| Deliverables in 2024: | 80% of external debt orders to be realized electronically 2 new employments in PDMD Adopted procedure for Quarterly debt reconciliation with foreign creditors |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  |  | PLANNED INPUTS |  |  |
|  |  |  | START qq/yy | END qq/yy |  |  |  |  |  |  |  | BUDGET |  | SOURCE |
| 1. Introducing e-banking with NBRNM for external debt repayment |  |  | 2024 | 2025 |  | Ministry of Finance |  |  | NBRNM |  |  | / |  | / |
| 2. Strengthening public debt management capacities |  |  | 2024 | 2027 |  | Ministry of Finance |  |  | Agency for administration |  |  | 9,500 |  | National Budget |
| 3. Reconciling the debt stock with the creditors |  |  | 2024 | 2024 |  | Ministry of Finance |  |  | Multilateral, bilateral and private creditors |  |  | / |  | / |
| MEASURE 2: Increasing public debt transparency |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  | Target FY 2024 |  |  | Target FY 2025 |  |  | Target FY 2025 |  |  | Target FY 2026 |
| Transparent presentation of public debt in line with international methodologies and standards | Calculation of general government debt in accordance with the statistical standard SDDS plus |  |  |  | Government debt is displayed according to SDDS plus standard |  |  | / |  |  | / |  |  | / |
|  | Publication of general government debt in accordance with the Maastricht criterion |  |  |  | / |  |  | The general government debt is harmonized with the Maastricht criterion |  |  | / |  |  | / |
| Deliverables in 2024: | Government debt data aligned with definition for Maastricht debt |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  |  | PLANNED INPUTS |  |  |
|  |  |  | START qq/yy | END qq/yy |  |  |  |  |  |  |  | BUDGET |  | SOURCE |
| 1. Modifications and amendments to Public Debt Law to the end of aligning the debt definition with the Maastricht Criteria |  |  | 2024 | 2025 |  | MoF |  |  | EU, World bank |  |  | / |  | / |
| 2. Incorporating debt data in the Budget document |  |  | 2024 | 2027 |  | MoF |  |  | / |  |  | / |  | / |
| MEASURE 3: Introduction new debt instruments |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  | Target FY 2024 |  |  | Target FY 2025 |  |  | Target FY 2026 |  |  | Target FY 2027 |
| Expanding investors’ database | Diversification of debt instruments |  |  |  | Issuances of the Development Bond for citizens and the Green Bond will be defined during the monitoring process |  |  | Issuances of the Development Bond for citizens and the Green Bond will be defined during the monitoring process |  |  | Issuances of the Development Bond for citizens and the Green Bond will be defined during the monitoring process |  |  | Issuances of the Development Bond for citizens and the Green Bond will be defined during the monitoring process |
| Deliverables in 2024: | New issuances of Development Bond for citizens and the Green Bond |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  |  | PLANNED INPUTS |  |  |
|  |  |  | START qq/yy | END qq/yy |  |  |  |  |  |  |  | BUDGET |  | SOURCE |
| 1. Issuing Development Bond for Citizens |  |  | 2024 | 2027 |  | MoF |  |  | Citizens |  |  | / |  |  |
| 2. Issuing of Green bonds on domestic market |  |  | 2024 | 2027 |  | MoF |  |  | Development Bank |  |  | / |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | TOTAL: |  | EUR 9,500 |

| PILLAR: II: Revenue Mobilisation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PRIORITY 1: Tax and Customs Policy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Priority outcomes | Priority indicators | Target FY 2024 |  |  |  |  | Target FY 2025 |  |  | Target FY 2026 |  |  |  | Target FY 2027 |  |
| Legislation in the area of taxation and customs harmonized with the Union acquis, standards and best practices and with the country tax policy strategic framework | Progress made toward fulfilment of the EU accession criteria (steady progress in the respective Chapters 16 and 29) | Ch.29: Good level of preparation Good progress Ch.16: Moderately prepared Some progress |  |  |  |  | Ch.29: Good level of preparation Good progress Ch.16: Moderately prepared Good progress |  |  | Ch.29: Good level of preparation Very Good progress Ch.16: Good level of preparation Good progress |  |  |  | Ch.29: Good level of preparation Very Good progress Ch.16: Good level of preparation Good progress |  |
| MEASURE 1: Improved revenue legislation framework, harmonized with the EU acquis and best practices |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  | Target FY 2024 |  |  | Target FY 2025 |  |  | Target FY 2026 |  | Target FY 2027 |  |  |
| Objective is to improve and harmonize legislation in line with the relevant EU acquis and the best practices in the area of tax and customs legislation | Number of legislative acts (regarding Ch.16 And Ch.29) |  |  |  | Not less then 3 legislative acts |  |  | Not less then 3 legislative acts |  |  | Not less then 4 legislative acts |  | Not less then 5 legislative acts |  |  |
| Deliverables in 2024: | Prepared gap analyses and drafted new legal acts or amendments to the existing national tax and customs legislation (laws and by-laws) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  |  | PLANNED INPUTS |  |  |  |
|  |  |  | START qq/yy | END qq/yy |  |  |  |  |  |  |  | BUDGET |  |  | SOURCE |
| 1. Gap analysis of the national tax and customs legislation (laws and by-laws) compared to the EU legislation and best practices. |  |  | K1/24 | 2027 |  | MoF – Public Revenues and Tax and Customs Policy Department |  |  | PRO and CA |  |  | EUR 250,000 (budgeted amount for both activities 1 & 2) |  |  | Twinning Light Project Further harmonization of the tax legislation with the EU Acquis |
| 2. New legal acts and/or amendments to the existing national tax and customs legislation (laws and by-laws) drafted in line with the EU legislation and best practices |  |  | K1/24 | 2027 |  |  |  |  | PRO and CA |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | TOTAL: |  |  | EUR 250,000 |

| PILLAR II: Revenue Mobilization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PRIORITY 2: Tax Administration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Priority outcomes | Priority indicators | Target FY 2024 |  |  |  |  | Target FY 2025 |  |  | Target FY 2026 |  |  | Target FY 2027 |  |  |
| Improved stability, efficiency and quality of the revenue collection system (IT system) | % percentage of digitized tax services | 90% |  |  |  |  | 92% |  |  | 95% |  |  | 100% |  |  |
| More effective and efficient management of the overdue tax debt | improved rate of tax payment on time (VAT) | Rate on number of timely payments – 65% Rate on amount of timely payments - 75% |  |  |  |  | Rate on number of timely payments – 70% Rate on amount of timely payments - - 80% |  |  | Rate on number of timely payments – 80% Rate on amount of timely payments - 85% |  |  | Rate on number of timely payments – 90% Rate on amount of timely payments - 90% |  |  |
|  | Improved age structure of the tax debt (VAT) - reduced share of the debt older than 12 months in the total tax debt | Share of VAT debt (principal debt) over 12 months old in the total VAT debt at the end of FP - 70% |  |  |  |  | Share of VAT debt (principal debt) over 12 months old in the total VAT debt at the end of FP - 63% |  |  | Share of VAT debt (principal debt) over 12 months old in the total VAT debt at the end of FP - 56% |  |  | Share of VAT debt (principal debt) over 12 months old in the total VAT debt at the end of FP - 50% |  |  |
| Fully established systematic process for managing tax compliance risks | Increased number of taxpayers who voluntarily comply | Percentage of timely submitted returns and taxes payment compared to the previous year |  |  |  |  | Percentage of timely submitted returns and taxes payment compared to the previous year |  |  | Percentage of timely submitted returns and taxes payment compared to the previous year |  |  | Percentage of timely submitted returns and taxes payment compared to the previous year |  |  |
| MEASURE 1: Strengthen administrative capacity for better revenue collection and tax compliance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  | Target FY 2024 |  |  | Target FY 2025 |  |  | Target FY 2026 |  |  |  | Target FY 2027 |
| Improve tax revenue services, including tax collection and compliance, and overall establish a model for a professional service to taxpayers, recognizable for its best practices and quality standards | Increasing the amount of the established tax guarantee |  |  |  | Increase the amount of the established tax guarantee by 10% compared to 2023. |  |  | Increase the amount of the established tax guarantee by 10% compared to 2024. |  |  | Increase the amount of the established tax guarantee by 5% compared to 2025. |  |  |  | Increase the amount of the established tax guarantee by 5% compared to 2026. |
|  | Increasing the collection of tax debt based on an established tax guarantee |  |  |  | Increase in the amount of debt collected based on the established tax guarantee by 5% compared to 2023. |  |  | Increase in the amount of debt collected based on the established tax guarantee by 10% compared to 2024. |  |  | Increase in the amount of debt collected based on the established tax guarantee by 10% compared to 2025. |  |  |  | Increase in the amount of debt collected based on the established tax guarantee by 5% compared to 2026. |
|  | Value of collectible core tax arrears in FY end in percent of total core tax revenue collection for FY |  |  |  | VAT debt / VAT income ratio 16% |  |  | VAT debt / VAT income ratio 14% |  |  | VAT debt / VAT income ratio 12% |  |  |  | VAT debt / VAT income ratio 10% |
|  | Increase in the amount of additionally determined tax with audit compared to the previous year |  |  |  | Additional tax assessed per audit program increased per 3% compared to the results from the previous year |  |  | Additional tax assessed per audit program increased per 3% compared to the results from the previous year |  |  | Additional tax assessed per audit program increased per 3% compared to the results from the previous year |  |  |  | Additional tax assessed per audit program increased per 3% compared to the results from the previous year |
| Deliverables in 2024: | Implemented measures and activities to strengthen "social" awareness of the tax responsibility of the founders and managers of companies and inter-institutional compliance in practicing the mechanisms for this responsibility Proposal for changes and additions to the Law on Tax Procedure (which are not related to the redesign of business processes) harmonized with the Ministry of Finance and launched in the adoption procedure Established and functional Tax Enforcement Center Adopted Plan to improve the compliance of the PRO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  |  | PLANNED INPUTS |  |  |  |
|  |  |  | START qq/yy | END qq/yy |  |  |  |  |  |  |  | BUDGET |  |  | SOURCE |
| 1.More effective and efficient management of overdue tax debt |  |  | 2024 | 2027 |  | PRO |  |  | / |  |  | 147.000 Euro |  |  | National Budget |
| 2.Improving the Compliance risk management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| MEASURE 2: Digital transformation of the PRO with the establishment of an Integrated Tax Information System (ITIS) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  | Target FY 2024 |  |  | Target FY 2025 |  |  | Target FY 2026 |  |  |  | Target FY 2027 |
| The purpose of the measure is to build the capacity of the tax administration to administer tax revenues and contributions by strengthening administrative resources, more effective and efficient management of overdue tax debt and compliance risk management | Number of institutions with which the Integrated Tax Information System exchanges information |  |  |  | 26 |  |  | 27 |  |  | 28 |  |  | at least 30 |  |
| Deliverables in 2024: | - Conducted public procurement for software and hardware for e-invoicing and e-commerce - Prepared specification and technical documentation for public procurement for the development and upgrade of subsystems of an Integrated Tax Information System to support the tax functions of the PRO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  |  | PLANNED INPUTS |  |  |  |
|  |  |  | START qq/yy | END qq/yy |  |  |  |  |  |  |  | BUDGET |  |  | SOURCE |
| 1.Completion of the remaining modules of the Integrated Tax Information System |  |  | 2024 | 2027 |  | PRO |  |  | / |  |  | 2,430,000 |  |  | National Budget |
| 2.Ensuring IS security (Information System) and smooth functioning of the integrated tax information system |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | TOTAL: |  |  | EUR 2,577,000 |

| PILLAR II: Revenue mobilization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PRIORITY 3: Customs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Priority outcomes | Priority indicators | Target FY 2024 |  |  |  |  | Target FY 2025 |  |  | Target FY 2026 |  |  |  | Target FY 2027 |  |  |
| Availability of innovative equipment and training of staff for detection and control for the purpose of: control without disturbance, detection of hidden objects on persons, radiation detection, sampling and analysis of samples, manual search | Percentage of physical controls that resulted in the detection of irregularities in relation to the total number of performed physical controls using the new equipment | 10% of the total number of performed physical controls using the new equipment |  |  |  |  | 15% of the total number of performed physical controls using the new equipment |  |  | 15% of the total number of performed physical controls using the new equipment |  |  |  | 15% of the total number of performed physical controls using the new equipment |  |  |
| Introduction of a complete paperless environment in the customs procedure, through the implementation of electronic systems from the e-Customs program, i.e. the Multiannual Strategic Plan of the EU (MASP), compatible with the systems and procedures in the European Union; preparation for interconnection and interoperability with EU systems and implementation of systems compliant with EU systems (which may be established prior to EU accession) and staffing with appropriate hardware for those systems. | Implemented at least two (2) new IT systems / modules from the EU Multiannual Strategic Plan (MASP) at national level on appropriate hardware (ICS2 and e-commerce) | / |  |  |  |  | / |  |  | / |  |  |  | 2 |  |  |
| MEASURE 1: Strengthening joint control mechanisms and capacities in order to combat illegal trade and organized crime |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  | Target FY 2024 |  |  | Target FY 2025 |  |  | Target FY 2026 |  | Target FY 2027 |  |  |  |
| The purpose of the measure is to suppress illegal trade and organized crime, protect the legal economy, ensure safety and security, protect the health and safety of citizens and protect the environment. | Percentage of staff employed in the corresponding units for customs control actively using the new equipment |  |  |  | 30% |  |  | 70% |  |  | 70% |  |  |  | 70% |  |
| The purpose of the measure is to suppress illegal trade and organized crime, protect the legal economy, ensure safety and security, protect the health and safety of citizens and protect the environment. | Conducted appropriate professional trainings for the employees in the operational services for control and prosecution for fight against illicit trade and crime (number of events) |  |  |  | additional equipment will be procured |  |  | 5 |  |  | 5 |  |  |  | 7 |  |
| Deliverables in 2024: | - Preepare documents for the procurement of equipment, and organize procurement - Organize training for the emplyees |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  |  | PLANNED INPUTS |  |  |  |  |
|  |  |  | START qq/yy | END qq/yy |  |  |  |  |  |  |  | BUDGET |  |  |  | SOURCE |
| 1.Equipping with modern and reliable control equipment and appropriate training for employees, in order to protect financial and economic interests, guarantee the safety and security of citizens, environmental protection and protection from unfair and illicit trade |  |  | 2024 | 2027 |  | Customs Administration |  |  | EU - and its institutions, UN, Bilateral Cooperation, relevant domestic institutions |  |  | 2,000,000 |  |  |  | IPA2 and IPA3) |
| MEASURE 2: Modernization of customs services and their digitalization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  | Target FY 2024 |  |  | Target FY 2025 |  |  | Target FY 2026 |  | Target FY 2027 |  |  |  |
| By achieving this goal through modernization and continuation of the digitalization process, and at the same time by following the recommendations for harmonization and association with the EU, the system of public finances, fiscal discipline and efficiency in the management and use of public resources will be strengthened, transparency will be promoted and efficient services and economic development will be provided | Average yearly technical availability of the new customs IT systems for interconnectivity with the EU systems |  |  |  | 95% |  |  | 95% |  |  | 95% |  |  |  | 95% |  |
|  | Conducted appropriate professional trainings for the employees of the Customs Administration and the economic operators for implementation of systems (number of events) |  |  |  | 10 |  |  | 12 |  |  | 15 |  |  |  | 20 |  |
| Deliverables in 2024: | - Introduce a new computerised system (NCTS version 5) - Train the employess and the economic operators to use the application and the relevant legislation for its use - Prepare tender documents and launch tender for two EU related IT systems - Procure hardware |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  |  | PLANNED INPUTS |  |  |  |  |
|  |  |  | START qq/yy | END qq/yy |  |  |  |  |  |  |  | BUDGET |  |  |  | SOURCE |
| 1. Implementation of modern systems in order to comply with the Multiannual Strategic Plan of the EU (MASP), integration with European systems and procurement of appropriate hardware. |  |  | 2024 | 2027 |  | Customs Administration |  |  | EU |  |  | 4,000,000 |  |  |  | National Budget IPA 3 and Government of Korea |
| MEASURE 3: Adequate monitoring of excise good sand collection of excise duties |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  | Target FY 2024 |  |  | Target FY 2025 |  |  | Target FY 2026 |  | Target FY 2027 |  |  |  |
| The goal of this measure is through introduction of procedures and instruments for appropriate monitoring of excise goods, to combat against illicit trade in tobacco products and to increase collection of excise duties. Adequate monitoring of excise goods is important due to the increased volume of trade in such goods, the harm to health (especially found in tobacco products), registered tax evasion, illicit trade in excise goods as a source of financing for organized crime. | Preparation of a legal framework for implementing the TRACK&TRACE system |  |  |  | Signing the necessary Protocols between concerned institutions |  |  |  |  |  |  |  |  |  | High preparation for implementing the TRACK&TRACE system |  |
| Deliverables in 2024: | - Prerpearing necessary Protocols between concerned institutions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  |  | PLANNED INPUTS |  |  |  |  |
|  |  |  | START qq/yy | END qq/yy |  |  |  |  |  |  |  | BUDGET |  |  |  | SOURCE |
| 1 Establishing a system for marking and tracking tobacco products (cigarettes) through the TRACK&TRACE system |  |  | 2024 | 2027 |  | Customs Administration |  |  |  |  |  | Funding cannot be planned at the moment |  |  |  | Funding cannot be planned at the moment |
|  |  |  |  |  |  |  |  |  |  |  |  | TOTAL: |  |  |  | EUR 6,000,000 |

| PILLAR III: Planning and Budget |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PRIORITY 1: Budget Planning |  |  |  |  |  |  |  |  |  |  |  |  |
| Priority outcomes | Priority indicators | Target FY 2024 |  |  |  |  | Target FY 2025 |  |  | Target FY 2026 |  | Target FY 2027 |
| Predictable and reliable budget allocations for budget organisations considering colsolidation in public spending and reducing the budget deficit. | Deviation between the original estimates and actual outturns | -3,4% of GDP |  |  |  |  | -3% of GDP |  |  | -3% of GDP |  | -2,8% of GDP |
| MEASURE 1: Improving medium-term planning |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  | Target FY 2024 |  |  | Target FY 2025 |  |  | Target FY 2026 | Target FY 2027 |
| Improving medium-term planning | Changes in relation to the initial projections / achievements (Fiscal deficit) |  |  |  | 0,1% |  |  | 0,1% |  |  | 0,09% 0,09% |  |
| Deliverables in 2024: | Medium-Term Fiscal Strategy based on a sectoral approach |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  | PLANNED INPUTS |  |
|  |  |  | START qq/yy | END qq/yy |  |  |  |  |  |  | BUDGET | SOURCE |
| 1. Medium-Term Fiscal Strategy based on a sectoral approach |  |  | 2024 | 2027 |  | Ministry of Finance/Budget Department |  |  | Budget users |  | / |  |
| 2. Determination of medium term expednitures celiings |  |  | 2024 | 2027 |  | Ministry of Finance/Budget Department |  |  | Budget users |  | / |  |
| 3. Strengthening medium-term planning at public enterprises and companies at central level |  |  | 2024 | 2027 |  | Ministry of Finance/Budget Department |  |  | Budget users |  | / |  |
| MEASURE 2: Improving sectoral approach of budget planning and development and implementation of bylaws |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  | Target FY 2024 |  |  | Target FY 2025 |  |  | Target FY 2026 | Target FY 2027 |
| Improved Budget Planning | Number of First level of budget users |  |  |  | Around 100 |  |  | Around 50 |  |  | Less than 50 | Less than 50 |
| Deliverables in 2024: | By-laws and types of classifications |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  | PLANNED INPUTS |  |
|  |  |  | START qq/yy | END qq/yy |  |  |  |  |  |  | BUDGET | SOURCE |
| 1. Preparing and implementing OBL bylaws |  |  | 2024 | 2027 |  | Ministry of Finance |  |  | Budget users |  | EUR 218,000 | US Treasury |
| 2. Preparing and implementing several types of classifications - administrative/organizational, economic, program, functional classifications, as well as classification of sources of financing |  |  | 2024 | 2027 |  | Ministry of Finance/Budget Department |  |  | Budget users |  | EUR 164,000 | US Treasury |
| 3. Strengthening of capacities, training of employees of the MoF and budget beneficiaries |  |  | 2024 | 2027 |  | Ministry of Finance/Budget Department |  |  | Budget users |  | EUR 245,000 | US Treasury |
| MEASURE 3: Introducing performance based budget (value for money) |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  | Target FY 2024 |  |  | Target FY 2025 |  |  | Target FY 2026 | Target FY 2027 |
| Developing of multi-year indicators | Share of capital in total expenditures |  |  |  | 14,8% |  |  | 15% |  |  | 16,1% | 16,6% |
| Deliverables in 2024: | Upgreating content of Fiscal Strategy |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  | PLANNED INPUTS |  |
|  |  |  | START qq/yy | END qq/yy |  |  |  |  |  |  | BUDGET | SOURCE |
| 1. Developing of multi-year indicators for measuring the success in the implementation of budget policies |  |  | 2024 | 2027 |  | Ministry of Finance and Government |  |  | Budget users/PE/JSC/LSGu |  | EUR 27,000 | US Treasury |
|  |  |  |  |  |  |  |  |  |  |  | TOTAL: | EUR 654,000 |

| PILLAR III: Planning and Budget |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PRIORITY 2: Strengthened Public Investment Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Priority outcomes | Priority indicators | Target FY 2024 |  |  |  |  | Target FY 2025 |  |  | Target FY 2026 |  |  |  | Target FY 2027 |  |
| Efficient and effective planning, selection, budgeting and implementation of major public investment projects | PEFA score for indicator PI - 11.Public Investment Management 11.1. Economic analysis of investment projects 11.2. Investment project selection 11.3. Investment project costing 11.4. Investment project monitoring | - |  |  |  |  |  |  |  | - |  |  |  | PEFA Score PI-11: >C 11.1) >C 11.2) >C 11.3) >C 11.4) >C - |  |
| MEASURE 1: Efficient coordination and development of public investment management processes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  | Target FY 2024 |  |  | Target FY 2025 |  |  | Target FY 2026 |  | Target FY 2027 |  |  |
| Established structured and comprehensive approach to decision making for public investment projects | 1) Staff capacity of the PIM Department in the MoF 2) Supporting legal framework for PIM adopted |  |  |  | 1) 70% of planned staff engaged 2) 2 acts adopted |  |  | 1) 90% of planned staff engaged 2) Number of new acts adopted |  |  | 1) 100% of planned staff engaged |  | 1) 100% of planned staff engaged |  |  |
| Deliverables in 2024: | - PIM Decree - Manual for PIM processes - Staffing of PIM department (10 employees) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  |  | PLANNED INPUTS |  |  |  |
|  |  |  | START qq/yy | END qq/yy |  |  |  |  |  |  |  | BUDGET |  |  | SOURCE |
| 1.Strengthen the supporting legal framework for PIM |  |  | 2024 | 2025 |  | MoF |  |  | External expertise (WB/IMF/EU) |  |  | 15,000 |  |  | External funding |
| 2.Strengthen the institutional capacity of the MoF in the PIM system |  |  | 2024 | 2027 |  | MoF |  |  | External expertise (WB/IMF/EU) |  |  | 64,000 10,000 |  |  | National Budget External funding |
| MEASURE 2: Established single pipeline of appraised capital public investment projects |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  | Target FY 2024 |  |  | Target FY 2025 |  |  | Target FY 2026 |  | Target FY 2027 |  |  |
| Capital spending is allocated to the most productive sectors and projects by a comprehensive, unified, and medium-term perspective to capital budgeting, as well as objective criteria and competitive procedures for selecting particular investment projects. | Single pipeline of appraised capital public investment projects established |  |  |  | Мethodology for pre-appraisal, appraisal, prioritization of public investment project adopted |  |  | Standard criteria for project selection/ prioritization adopted |  |  | All budget users at central and local level prepare public investment proposals following the PIM methodology |  | Developed single pipeline of appraised capital public investment projects |  |  |
| Deliverables in 2024: | - Guidelines (methodology) for feasibility study - Standard criteria for project selection/ prioritization - Trainings |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  |  | PLANNED INPUTS |  |  |  |
|  |  |  | START qq/yy | END qq/yy |  |  |  |  |  |  |  | BUDGET |  |  | SOURCE |
| 1. Develop general public investment project appraisal methodology |  |  | 2024 | 2025 |  | MoF |  |  | External expertise (WB/EU)) |  |  | 20,000 |  |  | External funding |
| 2. Establish standard criteria for project selection/ prioritization |  |  | 2024 | 2025 |  | MoF, Government |  |  | External expertise (WB/EU)) |  |  | 10,000 |  |  | External funding |
| 3. Provide training to MoF professionals on project appraisal and review of preinvestment studies |  |  | 2024 | 2027 |  | MoF, Government |  |  | External expertise (WB/IMF/EU) |  |  | 20,000 |  |  | External funding |
| 4. Provide training to budget users/SoEs/LSGUs professionals on project formulation appraisal and selection |  |  | 2024 | 2027 |  | MoF |  |  | BU/SoEs/ LSGUs External expertise (WB/EU) |  |  | 10,000 |  |  | External funding |
| MEASURE 3: Efficient and effective monitoring of capital investments |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  | Target FY 2024 |  |  | Target FY 2025 |  |  | Target FY 2026 |  | Target FY 2027 |  |  |
| Improved project monitoring and reporting arrangements for major public investment projects thus ensuring value for money. | - Created database of public investment projects from which to select budget candidates and monitor financial implementation of projects - Number of monitoring reports for the public investment portfolio prepared |  |  |  | / |  |  | - Developed short - term IT solution that will provide the MoF with a database of projects - 1 |  |  | 1) / 2) 2 |  | 1) / 2) 2 |  |  |
| Deliverables in 2024: | -Procedure for monitoring and ex-post review of projects; -Monitoring reports on the national investment portfolio; -Short-term IT solution for PIM (PIMIS). |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  |  | PLANNED INPUTS |  |  |  |
|  |  |  | START qq/yy | END qq/yy |  |  |  |  |  |  |  | BUDGET |  |  | SOURCE |
| 1. Introduce procedures for risk-based centralized monitoring |  |  | 2024 | 2027 |  | MoF |  |  | External expertise (WB/ IMF/EU) |  |  | 25,000 |  |  | External funding |
| 2. Develop a short-term IT solution for PIM |  |  | 2024 | 2025 |  | MoF |  |  | External expertise (IMF) |  |  | 50,000 |  |  | External funding |
|  |  |  |  |  |  |  |  |  |  |  |  | TOTAL: |  |  | EUR 224,000 |

| PILLAR III: Planning and Budget |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PRIORITY 3: Strengthen the accounting of budgets and budget users |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Priority outcomes | Priority indicators | Target FY 2024 |  |  |  |  | Target FY 2025 |  |  | Target FY 2026 |  |  |  | Target FY 2027 |  |
| Improved financial reporting by establishing new accounting practices | Percentage of budget users applying new accounting practices. | 0 |  |  |  |  | 0 |  |  | 50% of budget users apply new accounting practices |  |  |  | 100% of budget users apply new accounting practices |  |
| MEASURE 1: Strengthening the accounting system by applying new accounting practices |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  | Target FY 2024 |  |  | Target FY 2025 |  |  | Target FY 2026 |  | Target FY 2027 |  |  |
| Determining the strategic direction for the development of new accounting practices | Adoption of new accounting standards |  |  |  | Adoption a Strategy for Improvement of the Budget Institution’s Accounting with a gap analysis, setting priorities, goals and action plan and аadoption of amendments of the Law on accounting of budgets and budget users. |  |  | New regulatory framework on accounting of budgets and budget users and bylaws |  |  | Harmonizing budget information systems and budget users with the new accounting requirements |  | Harmonizing budget information systems and budget users with the new accounting requirements |  |  |
| Deliverables in 2024: | Adoption a Strategy for Improvement of the Budget Institution’s Accounting with a gap analysis, setting priorities, goals and action plan and adoption of amendments of the Law on accounting of budgets and budget users |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  |  | PLANNED INPUTS |  |  |  |
|  |  |  | START qq/yy | END qq/yy |  |  |  |  |  |  |  | BUDGET |  |  | SOURCE |
| 1. Adoption a Strategy for Improvement of the Budget Institutions’s Accounting with a gap analysis, setting priorities and goals and action plan and amendments of the Law on accounting of budgets and budget users |  |  | June 2024 | December 2024 |  | MoF |  |  |  |  |  | 10,000 |  |  | UNDP |
| MEASURE 2. Capacity building of public sector accountants |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  | Target FY 2024 |  |  | Target FY 2025 |  |  | Target FY 2026 |  | Target FY 2027 |  |  |
| Capacity building of public sector accountants | Number of certified public sector accountants |  |  |  | 80 certified accountants |  |  | 150 certified accountants |  |  | 220 certified accountants |  | 350 certified accountants |  |  |
| Deliverables in 2024: | Certified accountants in public sector |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  |  | PLANNED INPUTS |  |  |  |
|  |  |  | START qq/yy | END qq/yy |  |  |  |  |  |  |  | BUDGET |  |  | SOURCE |
| 1.Preparing training and exam curriculum for public sector accountants |  |  | June 2024 | December 2025 |  | MoF |  |  | Universities |  |  | / |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | TOTAL: |  |  | EUR 10,000 |

| PILLAR: IV PUBLIC PROCUREMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PRIORITY 1: Public Procurement Policy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Priority outcomes | Priority indicators | Target FY 2024 |  |  |  |  | Target FY 2025 |  |  | Target FY 2026 |  |  | Target FY 2027 |  |
| Improved public procurement process | - percentage of one bid tenders | ≤29% |  |  |  |  | ≤28% |  |  | ≤27% |  |  | ≤ 26% |  |
|  | - percentage of cancelled procedures | ≤21% |  |  |  |  | ≤19,5% |  |  | ≤19% |  |  | ≤ 18,5 % |  |
|  | - number of appeals | Reduction by 0.5% of appeals |  |  |  |  | Reduction by 1% of appeals |  |  | Reduction by 1.5% of appeals |  |  | Reduction by 2% of appeals |  |
|  | - number of appeals before both the Administrative Court and the Higher Administrative Court | Reduction by 5% of the annulled Decisions of SAC |  |  |  |  | Reduction by 5% of the annulled Decisions of SAC |  |  | Reduction by 5% of the annulled Decisions of SAC |  |  | Reduction by 5% of the annulled Decisions of SAC |  |
| MEASURE 1: Improving the cooperation among the key institutions in the public procurement system |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  | Target FY 2024 |  |  | Target FY 2025 |  |  | Target FY 2026 | Target FY 2027 |  |  |
| Timely identification of gaps and irregular implementation of PPL, aiming to prevent irregularities and support duly and uniform implementation of the law | - Held working meetings |  |  |  | Held at least 2 meetings |  |  | Held at least 2 meetings |  |  | Held at least 2 meetings | Held at least 2 meetings |  |  |
| Deliverables in 2024: | Working meetings at regular basis |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  | PLANNED INPUTS |  |  |  |
|  |  |  | START qq/yy | END qq/yy |  |  |  |  |  |  | BUDGET |  |  | SOURCE |
| Regular communication and coordination of Advisory group of the key institutions in the procurement system |  |  | Q1/2024 | Q4/2027 |  | PPB |  |  | SAC, SAO, CPC, SCPC, ME |  | - |  |  | - |
|  |  |  |  |  |  |  |  |  |  |  | TOTAL: |  |  | EUR 84,000 |
| MEASURE 2: Combating corruption in public procurement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  | Target FY 2024 |  |  | Target FY 2025 |  |  | Target FY 2026 | Target FY 2027 |  |  |
| Introducing anti-corruption practices in public procurement cycle | - Template of Statement for impartiality and confidentiality (SI&C) |  |  |  | Template of SI&C published on PPB |  |  | - |  |  | - | - |  |  |
| Deliverables in 2024: | Template of Statement for impartiality and confidentiality |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  | PLANNED INPUTS |  |  |  |
|  |  |  | START qq/yy | END qq/yy |  |  |  |  |  |  | BUDGET |  |  | SOURCE |
| Introducing documents for strengthening the integrity of the procurement process |  |  | Q1/2024 | Q1/2025 |  | PPB |  |  | - |  | - |  |  | - |
| MEASURE 3: Introducing new system for education within PPB |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  | Target FY 2024 |  |  | Target FY 2025 |  |  | Target FY 2026 | Target FY 2027 |  |  |
| Improve the knowledge and skills of public procurement officers | - Established new system for education within PPB |  |  |  | - |  |  | - |  |  | Established new system for education within PPB | 15 organized trainings according new established system for education within PPB |  |  |
| Deliverables in 2024: | Revision of the Programme for education with recommendations; |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  | PLANNED INPUTS |  |  |  |
|  |  |  | START qq/yy | END qq/yy |  |  |  |  |  |  | BUDGET |  |  | SOURCE |
| Revision of the programme for education |  |  | Q1/2024 | Q4/2026 |  | PPB |  |  | MF |  | - |  |  | - |
| MEASURE 4: Increasing the administrative capacities of the SAC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  | Target FY 2024 |  |  | Target FY 2025 |  |  | Target FY 2026 | Target FY 2027 |  |  |
| Ensure sufficient capacity of SAC for timely processing of appeals | - Number of new employments in SAC |  |  |  | 5 new employees |  |  | - |  |  | - | - |  |  |
| Deliverables in 2024: | New employees in SAC |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  | PLANNED INPUTS |  |  |  |
|  |  |  | START qq/yy | END qq/yy |  |  |  |  |  |  | BUDGET |  |  | SOURCE |
| Increasing the number of employees in SAC |  |  | Q1/2024 | Q1/2025 |  | SAC |  |  | MF |  | 84.000 EUR |  |  | National budget |
|  |  |  |  |  |  |  |  |  |  |  | TOTAL: |  |  | EUR 84,000 |

| PILLAR: IV Public Procurement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PRIORITY 2: Public Private Partnership and Concessions on goods of general interest |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Priority outcomes | Priority indicators | Target FY 2024 |  |  |  |  | Target FY 2025 |  |  | Target FY 2026 |  |  |  | Target FY 2027 |  |
| Unification and digitalization of the process of awarding contracts for establishing public-private partnership, increased transparency and efficiency in the implementation of the Law on Public-Private Partnership and strengthening and developing the capacities of the Ministry of Economy for consistent realization of competencies according to law. | 1)Number of concluded agreements for establishing a public-private partnership 2) Effective and consistent implementation of the obligations of the contracting parties in accordance with the agreements for establishment of public-private partnership. | / |  |  |  |  | 1) Potential increase in the number of concluded contracts for public-private partnership by 5% compared to the number of contracts concluded in the year as a basis for monitoring 2) Potential reduction by 20% of concluded contracts for public-private partnership in which certain legal obstacles in the realization occurred, compared to the percentage of contracts concluded in the year as a basis for monitoring |  |  | 1) Potential increase in the number of concluded public-private partnership agreements by 5% compared to the previous year 2) Potential reduction by 10% of concluded public-private partnership agreements in which certain legal obstacles in the realization occurred, compared to the previous year |  |  |  | 1) Potential increase in the number of concluded public-private partnership agreements by 5% compared to the previous year 2) Potential reduction by 10% of concluded public-private partnership agreements in which certain legal obstacles in the realization occurred, compared to the previous year |  |
| MEASURE 1: Establishment of the Unique Electronic System Public Private Partnership System (UESPPP) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  | Target FY 2024 |  |  | Target FY 2025 |  |  | Target FY 2026 |  | Target FY 2027 |  |  |
| 1)Commissioning of the UESPPP and the Register of awarded contracts for the establishment of a public-private partnership and its functionality 2)Percentage of PPP contracts whose progress in implementation is regularly reported to the system within the deadlines provided by the law 3)Percentage of initiated procedures for awarding a contract for establishing a public-private partnership, which have not been completed |  |  |  |  |  |  |  | 1)Establishment of the UESPPP and start of implementation - The software solution for the establishment of the UESPP and the Register of awarded contracts for the establishment of a public-private partnership have been prepared 2) 50% of the public-private partnership agreements, which progress of the implementation is regularly reported in the system within the deadlines provided by law 3)Reduction by 10% of the initiated procedures for awarding a contract for establishing a public-private partnership, which are not completed, compared to the percentage of initiated but not completed procedures in the year as a basis for monitoring |  |  | 1) 70% of the public-private partnership agreements, which progress of implementation is regularly reported in the system within the deadlines provided by law 2) Reduction by 5% of the initiated procedures for awarding a contract for establishing a public-private partnership, which have not been completed, compared to the previous year |  | 1) 100% of the public-private partnership agreements, of which progress in the implementation is regularly reported in the system within the deadlines provided by law 2) Reduction by 5% of the initiated procedures for awarding a contract for establishing a public-private partnership, which have not been completed, compared to the previous year |  |  |
| Deliverables in 2024: | If the Law on public private partnership is adopted starting with the prparations for selection of an IT company for establishment of the SESPPP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  |  | PLANNED INPUTS |  |  |  |
|  |  |  | START qq/yy | END qq/yy |  |  |  |  |  |  |  | BUDGET |  |  | SOURCE |
| 1. Selection of an IT company for preparation of the Improving and upgrading the UESPPP and a Register of awarded contracts for the establishment of public-private partnership |  |  | 2024 | / |  | MoE |  |  |  |  |  | N/A |  |  | N/A |
| 2. Preparation and implementation of the software solution for the establishment of public-private partnership and a Register of awarded contracts the establishment of public-private partnership |  |  | 2024 | 2025 |  | МоЕ |  |  | PPB/MoF |  |  | Up To 500,000 eur |  |  | Financial gap |
| MEASURE 2: Completion of the legal and regulatory framework in the field of public-private partnership and Concession on Goods of General Interest |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  | Target FY 2024 |  |  | Target FY 2025 |  |  | Target FY 2025 |  | Target FY 2026 |  |  |
| Adoption of the bylaws by the Minister of Economy and the Minister of finance | Adoption of the bylaws that will arise from the Law on public private partnership by the Minister of economy. Adoption of the bylaws that will arise from the Law on concession on goods of general interest by the Minister of finance. |  |  |  |  |  |  | Publication of 13 bylaws in the Official Gazette of RNM which prescribe in more detail the rules for: Register of awarded contracts for establishing public-private partnership, UESPPP, criteria for preparation of PPP projects, Feasibility study, PPP agreements, planning reporting e.t.c. Publication of 2 bylaws in the Official Gazette of RNM which will arise of the Law on Concession on goods of general interest |  |  | Implementation of the bylaws |  | Implementation of the bylaws |  |  |
| Deliverables in 2024: | / |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  |  | PLANNED INPUTS |  |  |  |
|  |  |  | START qq/yy | END qq/yy |  |  |  |  |  |  |  | BUDGET |  |  | SOURCE |
| 1.Preparation and adoption of 13 bylaws that will arise from the Law on Public Private Partnership and preparation of the Guidline with exemples of PPP prjoects |  |  | 2024 | 2025 |  | MoE |  |  | Working group for preparation of the bylaws |  |  | EUR 11,000 |  |  | Financial gap |
| 2. Preparation and adoption of the bylaws that will arise from the f the Law on Concession on goods of general interest |  |  | 2024 | 2025 |  | MoF |  |  | MoE |  |  | / |  |  |  |
| MEASURE 3: Strengthening and developing the capacities of the Ministry of Economy in the field of public-private partnership |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  | Target FY 2024 |  |  | Target FY 2025 |  |  | Target FY 2026 |  | Target FY 2027 |  |  |
|  | Increasing the capacity and efficiency of the Public Private Partnership and Concessions Unit |  |  |  | Employment of 2 new civil servants - ratio of approved financial resources for employment from the Ministry of Finance versus the real employment needs in the Department for Public Private Partnership and Concessions and their training in the area of public private partnership. |  |  | Employment of 1 new civil servant - ratio of approved financial resources for employment from the Ministry of Finance versus the real employment needs in the Department for Public Private Partnership and Concessions and their training in the area of public private partnership |  |  | Development and improvement of the capacities of the employees in the Department for Public Private Partnership and Concessions |  | Development and improvement of the capacities of the employees in the Department for Public Private Partnership and Concessions |  |  |
| Deliverables in 2024: | Increased the number of employees in the Ministry of economy in the Public private partnership and concession Unit |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  |  | PLANNED INPUTS |  |  |  |
|  |  |  | START qq/yy | END qq/yy |  |  |  |  |  |  |  | BUDGET |  |  | SOURCE |
| 1. Increasing the number of employees in the Ministry of Economy and professional training for public-private partnership |  |  | 2024 | 2025 |  | MoE |  |  | MoF |  |  | 48,000 eur |  |  | National Budget |
|  |  |  |  |  |  |  |  |  |  |  |  | TOTAL: |  |  | EUR 559,000 |

| PILLAR V: Public finance digitalisation and continues learning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PRIORITY 1: Implementation of an Integrated Financial Management Information System (IFMIS) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Priority outcomes | Priority indicators | Target FY 2024 |  |  |  |  |  | Target FY 2025 |  |  | Target FY 2026 |  |  | Target FY 2027 |  |  |
| Improved operational efficiency and transparency through IFMIS in line with the new OBL. | The required time for the processing of payments through IFMIS and Treasury Single Account interface was reduced |  |  |  |  |  |  |  |  |  | On average, 15 days for entities to submit invoices to Treasury +1 day for payment processing by Treasury |  |  | 5 days for entities to submit invoices to Treasury +1 day for payment processing by Treasury |  |  |
|  | Comprehensiveness of publicly published general government reporting | IFMIS bidding process is launched including the requirements for necessary improvements in reporting. |  |  |  |  |  | IFMIS development is completed and the pilot implementation includes testing of reporting improvements |  |  | IFMIS is fully operational and new reporting capabilities are available. Government entities can generate reports including all relevant institutions. |  |  | Regulatory agencies, independent institutions PEs are included as part of the budget preparation and execution reports through the new IFMIS, in line with new PE Registry. |  |  |
|  | Open Budget Index Score (transparency) increased | 50 out of 100 (2023) |  |  |  |  |  |  |  |  |  |  |  | 61 out of 100 (2025) |  |  |
| MEASURE 1: Development of IFMIS as an integrated centralized web-based system supporting decentralized operations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  |  | Target FY 2024 |  |  | Target FY 2025 |  |  |  | Target FY 2026 |  |  | Target FY 2027 |
| - Development of new IFMIS application software and relevant GovTech solutions to operationalize the new OBL, as well as the new/enhanced PFM processes. | New IFMIS is operational |  |  |  |  | New IFMIS is being developed |  |  | IFMIS has gone live after being piloted |  |  |  | IFMIS is used in the preparation and execution of the central government budget |  |  | At least 95 percent of payments processed through the IFMIS |
| Deliverables in 2024: | The IFMIS Solution Provider has been chosen, marking the initiation of the development phase for IFMIS modules |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  |  | PLANNED INPUTS |  |  |  |
|  |  |  |  | START qq/yy | END qq/yy |  |  |  |  |  |  |  | BUDGET |  |  | SOURCE |
| 1.Selection of IFMIS Solution Provider |  |  |  | 2023 | 2024 |  | Ministry of Finance |  |  | BETAPFMI PIU |  |  | N/A |  |  | WB Loan (including EU contribution) |
| 2.Development of IFMIS modules and installation of hardware system and interfaces |  |  |  | 2024 | 2025 |  | Ministry of Finance |  |  | BETAPFMI PIU |  |  | N/A |  |  | WB Loan (including EU contribution) |
| 3.IFMIS pilot implementation and operational acceptance |  |  |  | 2024 | 2026 |  | Ministry of Finance |  |  | BETAPFMI PIU |  |  | N/A |  |  | WB Loan (including EU contribution) |
| MEASURE 2: Expansion of MoF ICT infrastructure (in line with whole-of-government approach) to host new IFMIS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  |  | Target FY 2024 |  |  | Target FY 2025 |  |  |  | Target FY 2025 |  |  | Target FY 2026 |
| New IFMIS will be a centralized web-based shared platform to support decentralized operations (online/offline) countrywide. This measure involves the expansion of the Ministry of Finance's (MoF) Information and Communication Technology (ICT) infrastructure, aligning with a comprehensive government-wide strategy, with primary objective to accommodate the implementation of the new IFMIS. | The percentage growth in the hosting capacity of MoF ICT infrastructure to support the implementation of new IFMIS |  |  |  |  | New data warehouse and BI tools developed and linked with the IFMIS. |  |  | / |  |  |  | / |  | Improved availability of the MDS and DRC |  |
| Deliverables in 2024: | New data warehouse and BI tools developed and linked with the IFMIS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  |  | PLANNED INPUTS |  |  |  |
|  |  |  |  | START qq/yy | END qq/yy |  |  |  |  |  |  |  | BUDGET |  |  | SOURCE |
| 1. Enhancement of the existing data centers and network connectivity |  |  |  | 2024 | 2027 |  | Ministry of Finance |  |  | BETAPFMI PIU |  |  | N/A |  |  | WB Loan (including EU contribution) |
| 2. Establishment of the secure backup network connections |  |  |  | 2024 | 2027 |  | Ministry of Finance |  |  | BETAPFMI PIU |  |  | N/A |  |  | WB Loan (including EU contribution) |
| MEASURE 3: Capacity strengthening training and change management to support OBL reforms and countrywide IFMIS operations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  |  | Target FY 2024 |  |  | Target FY 2025 |  |  |  | Target FY 2026 |  |  | Target FY 2027 |
| To support the establishment of new institutional structures needed for the implementation of the IFMIS and create a supportive enabling environment to ensure the success of the new model. | Improvement in user proficiency with the IFMIS following the capacity-strengthening training and change management initiatives |  |  |  |  | / |  |  | Assessment of user proficiency with the IFMIS and initiate capacity-strengthening training programs and change management initiatives |  |  |  | Training and Skill Development |  | Consolidation and Continuous Improvement |  |
| Deliverables in 2024: | No deliverables are planned for 2024 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  |  | PLANNED INPUTS |  |  |  |
|  |  |  |  | START qq/yy | END qq/yy |  |  |  |  |  |  |  | BUDGET |  |  | SOURCE |
| 1. Transition from existing MoF Systems to IFMIS |  |  |  | 2025 | 2027 |  | Ministry of Finance |  |  | BETAPFMI PIU |  |  | N/A |  |  | WB Loan (including EU contribution) |
| 2. Training of IFMIS users from central and local budget entities |  |  |  | 2025 | 2027 |  | Ministry of Finance |  |  | BETAPFMI PIU |  |  | N/A |  |  | WB Loan (including EU contribution) |
| 3. Development of a business continuity plan and disaster recovery skills for the MoF’s main data center and business continuity / disaster recovery center operations |  |  |  | 2025 | 2027 |  | Ministry of Finance |  |  | BETAPFMI PIU |  |  | N/A |  |  | WB Loan (including EU contribution) |
|  |  |  |  |  |  |  |  |  |  |  |  | TOTAL: |  |  | / |  |

| PILLAR V : Public finance digitalisation and continues learning |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PRIORITY 2: Public Finance Academy (Learning organisation) |  |  |  |  |  |  |  |  |  |  |
| Priority outcomes | Priority indicators | Target FY 2024 |  | Target FY 2025 |  |  | Target FY 2025 |  | Target FY 2026 |  |
| Provided continuous education in the field of public financial management. | Management's perception of whether the Academy adds value to their employees (low, medium or high level of value added perception) | Low |  | medium |  |  | High |  | high |  |
| MEASURE 1: Developing and implementing a curriculum |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: | Target FY 2024 |  | Target FY 2025 |  |  | Target FY 2026 |  | Target FY 2027 |  |
| Supporting the operations of the Academy by preparing appropriate methodological tools and a comprehensive Training Program. | Prepared annual training program and curricula | Training program and curricula prepared for 2024 |  | Training program and curricula prepared for 2025 |  |  | Training program and curricula prepared for 2026 |  | Training program and curricula prepared for 2027 |  |
|  | Satisfaction of the participants from the conducted trainings (low, medium or high level of satisfaction) | Medium |  | Medium |  |  | high |  | high |  |
|  | Number of organized trainings | 5 |  | 10 |  |  | 20 |  | 30 |  |
| Deliverables in 2024: | - Methodology for preparing annual training programme and curriculum -Satisfaction of the participants with the carried-out trainings (low, medium or high level of satisfaction); - Trainings |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  | TIMEFRAME |  | RESPONSIBLE INSTITUTION |  | OTHER INSTITUTIONS INVOLVED | PLANNED INPUTS |  |  |  |
|  |  | START qq/yy | END qq/yy |  |  |  |  | BUDGET |  | SOURCE |
| 1. Developing methodology for preparing annual training programme and curriculum |  | Q1/24 | Q4/24 | MoF |  | / |  | / |  | / |
| 2. Developing evaluation form for participants |  | Q1/24 | Q4/24 | MoF |  | Twinning project/donators |  | EUR 5,000 |  | EU twinning project |
| MEASURE 2: Developing of e-learning platform |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: | Target FY 2024 |  | Target FY 2025 |  |  | Target FY 2025 |  | Target FY 2026 |  |
| Developing of e-learning platform in order to make the trainings organized by the academy, easily accessible for all participants. | Number of organized trainings; |  | 1 |  | 4 |  | 8 |  | 12 |  |
| Deliverables in 2024: | Organized and implemented online trainings, providing learning materials |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  | TIMEFRAME |  | RESPONSIBLE INSTITUTION |  | OTHER INSTITUTIONS INVOLVED | PLANNED INPUTS |  |  |  |
|  |  | START qq/yy | END qq/yy |  |  |  |  | BUDGET |  | SOURCE |
| 1. Developing of the e – learning platform |  | Q1/24 | Q4/25 | MoF |  | Donators |  | EUR 25,000 |  | Donators |
| 2. Developing video tutorial and guidelines |  | Q1/24 | Q4/25 | MoF |  | Donators |  | / |  |  |
| 3. Organizing online trainings |  | Q1/24 | Q4/27 | MoF |  | Donators |  | / |  |  |
|  |  |  |  |  |  |  |  | TOTAL: |  | EUR 30,000 |

| PILLAR: VI - Public Internal Financial Control |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PRIORITY 1: Financial Management and Control |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Priority outcomes | Priority indicators | Target FY 2024 |  |  |  |  | Target FY 2025 |  |  | Target FY 2026 |  |  | Target FY 2027 |  |  |  |  |
| Prepared procedures for key financial management elements | Percentage of institutions that have applied the guidelines for risk management in their operations | 55 |  |  |  |  | 60 |  |  | 65 |  |  | 70 |  |  |  |  |
|  | Percentage of institutions that have delegated authorities and responsibilities for financial management and control | 50 |  |  |  |  | 60 |  |  | 70 |  |  | 80 |  |  |  |  |
|  | Percentage of implemented recommendations given during quality checks | 50 |  |  |  |  | 60 |  |  | 70 |  |  | 80 |  |  |  |  |
| MEASURE 1: Creating the conditions for improvement of a system of financial management based on risk management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  | Target FY 2024 |  | Target FY 2025 |  | Target FY 2026 |  |  | Target FY 2027 |  |  |  |  |  |
| Establishment of a comprehensive system of controls based on risk management, which guarantees the reasonable use of public funds by applying the principle of managerial accountability. | Prepared Simplified guideline for risk management process |  |  |  | Prepared and promoted of the new more practical and simplified guideline for risk management process |  | Trainings 2 |  | Traininigs 2 |  |  |  |  | Trainings 2 |  |  |  |
|  | Prepared practical guideline for managerial accountability |  |  |  | Prepared and promoted of the new practical guideline for managerial accountability |  | Trainings 2 |  | Trainings 2 |  |  |  |  | Trainings 2 |  |  |  |
|  | Strengthen the capacities of CHU |  |  |  | Employed a total of 10 people Trainings 4 |  | Employed a total of 12 people Trainings 4 |  | Employed a total of 13 people Trainings 4 |  |  |  |  | Employed a total of 14 people Trainings 4 |  |  |  |
| Deliverables in 2024: | - Simplified guideline for risk management process - Guideline for managerial accountability - Strengthened the CHU capacities (human resources/trainings/pilot quality checks) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  | OTHER INSTITUTIONS INVOLVED |  |  | PLANNED INPUTS |  |  |  |  |  |  |
|  |  |  | START qq/yy | END qq/yy |  |  |  |  |  |  | BUDGET |  |  |  | SOURCE |  |  |
| 1. Strengthen the capacity of the CHU to monitor and report on the functioning of the overall internal control system |  |  | Q1/24 | Q4/27 |  | MоF |  | / |  |  | 32,000 |  |  |  | Twinning project |  |  |
| 2. Preparation of the methodology for specific Financial Management and Control issues |  |  | Q1/24 | Q4/27 |  | MоF |  | / |  |  | 10,000 |  |  |  | National Budget |  |  |
|  |  |  |  |  |  |  |  |  |  | TOTAL: |  |  |  |  |  |  | EUR 42,000 |
| PILLAR: VI - Public Internal Financial Control |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PRIORITY 2 : Internal audit |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Priority outcomes | Priority indicators | Target FY 2024 |  |  |  |  | Target FY 2025 |  |  | Target FY 2026 |  |  | Target FY 2027 |  |  |  |  |
| Strengthened internal audit units that operate in line with the standards and that contributes to achievement of the goals of the public sector institutions | Number of internal auditors in the ministries | 50 |  |  |  |  | 60 |  |  | 65 |  |  | 70 |  |  |  |  |
|  | percentage of implemented recommendations given during quality checks | 50 |  |  |  |  | 60 |  |  | 70 |  |  | 80 |  |  |  |  |
|  | Percentage of certificated internal auditors | 45 |  |  |  |  | 60 |  |  | 70 |  |  | 80 |  |  |  |  |
|  | Percentage of implemented recommendations | 68 |  |  |  |  | 72 |  |  | 76 |  |  | 80 |  |  |  |  |
| MEASURE 1: Strengthening the quality of work of the internal audit units in the ministries |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  | Target FY 2024 |  | Target FY 2025 |  | Target FY 2026 |  |  | Target FY 2027 |  |  |  |  |  |
| Strengthening the quality of work of the internal audit units at the Ministries for the purpose of supporting the performance of their new tasks and duties as parent budget users. | Organized trainings for internal auditors; |  |  |  | 5 |  | 6 |  |  | 7 |  |  | 8 |  |  |  |  |
|  | Organized certification of internal auditors. |  |  |  | 1 |  | 2 |  |  | 2 |  |  | 2 |  |  |  |  |
|  | Strengthen the capacities of CHU |  |  |  | Employed a total of 10 people, Trainings 4 |  | Employed a total of 12 people12 Trainings 4 |  |  | Employed a total of 13 people Trainings 4 |  |  | Employed a total of 14 people Trainings 4 |  |  |  |  |
| Deliverables in 2024: | - Trainings for internal auditors - Certification of internal auditors. - Strengthened the CHU capacities (human resources/trainings/pilot quality checks) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  | OTHER INSTITUTIONS INVOLVED |  |  | PLANNED INPUTS |  |  |  |  |  |  |
|  |  |  | START qq/yy | END qq/yy |  |  |  |  |  |  | BUDGET |  |  |  | SOURCE |  |  |
| 1. Improving of Human Resources capacities of Internal Audit Units in the Ministries through adequate staffing and Continuous Professional Development at the internal auditors |  |  | Q1/24 | Q4/27 |  | MF |  | Ministries |  |  | 20,000 |  |  |  | National budget |  |  |
| 2. Strengthening CHU’s capacities for checking the quality of operations of the internal audit units |  |  | Q1/24 | Q4/27 |  | MF |  |  |  |  | 20,000 twininig project +12,000 national budget=32,000 |  |  |  | Twinning project and national budget |  |  |
| MEASURE 2: Improving the abilities to carry out performance and IT internal audits in the public sector institutions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  | Target FY 2024 |  | Target FY 2025 |  | Target FY 2026 |  |  |  |  |  |  | Target FY 2027 |  |
| Increasing the number of conducted performance audits and IT audits which will contribute to improving the work of central-level institutions | Prepared Guideline for performance internal audits |  |  |  | Prepared and promoted Guideline for performance internal audits |  | 4 |  | 4 |  |  |  |  | 4 |  |  |  |
|  | Prepared Guideline for IT internal audits |  |  |  | Prepared and promoted Guideline for IT internal audits |  | 4 |  | 4 |  |  |  |  | 4 |  |  |  |
|  | Increased number of conducted performance audits and IT audits |  |  |  | 6 |  | 10 |  | 14 |  |  |  |  | 18 |  |  |  |
| Deliverables in 2024: | - Guideline for performance internal audits; - Guideline for IT internal audits |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  | TIMEFRAME |  |  | RESPONSIBLE INSTITUTION |  | OTHER INSTITUTIONS INVOLVED |  |  | PLANNED INPUTS |  |  |  |  |  |  |
|  |  |  | START qq/yy | END qq/yy |  |  |  |  |  |  | BUDGET |  |  |  | SOURCE |  |  |
| 1.Preparation and promotion methodology for specific type of internal audits |  |  | Q1/24 | Q4/24 |  | MoF |  | / |  |  | / |  |  |  | / |  |  |
|  |  |  |  |  |  |  |  |  |  | TOTAL: |  |  |  |  |  |  | EUR 52,000 |

| PILLAR VII: External audit and parliamentary oversight |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PRIORITY 1: External Audit |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Priority outcomes | Priority indicators | Target FY 2024 |  |  |  | Target FY 2025 |  |  | Target FY 2026 |  |  |  | Target FY 2027 |
| Reduced tax evasion and increased fiscal discipline / increasing revenues in the Budget of RNM | Established amount of funds that have not been paid in the Budget of RNM | ≥ 16,000 euros |  |  |  | ≥ 11,000 euros |  |  | ≥ 9,000 euros |  |  |  | ≥ 7000 euros |
| Reduced tax evasion and increased fiscal discipline/increased revenues in the budgets of LSG and the City of Skopje | Established amount of funds that have not been paid into the Budget of the municipalities and the city of Skopje | ≥ 8,000 euros |  |  |  | ≥ 6,000 euros |  |  | ≥ 4,000 euros |  |  |  | ≥ 2,000 euros |
| Adhered principles when awarding public procurement contracts | Established amount of funds during the awarding of contracts for public procurement where irregularities were identified with the audits; | ≥ 8,100 euros |  |  |  | ≥ 7,500 euros |  |  | ≥ 7.300 euros |  |  |  | ≥7.000 euros |
| Scope of audits of LGUs and the City of Skopje, PE at the central and local level and JSC in state ownership | Number of covered audits of LGUs and the City of Skopje, PE at the central and local level and JSC in state ownership | ≥ 14 |  |  |  | ≥ 15 |  |  | ≥ 16 |  |  |  | ≥ 17 |
| MEASURE 1: Strengthen the legal framework for external audit |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  | Target FY 2024 |  |  | Target FY 2025 |  |  | Target FY 2026 |  |  | Target FY 2027 |
| Strengthen the constitutional, financial and operational independence of the SAO | Adopted amendments to the Constitution of RNM regulation of the SAO as a constitutional category |  |  | / |  |  | / |  |  | / |  |  | Adopted amendments to the Constitution of RNM for the regulation of SAO as a constitutional category |
|  | A new State Audit Law aims to strengthen the financial and operational independence of the SAO has been approved and adopted by the RNM Assembly |  |  | A new draft Law on State Audit to strengthen the financial and operational independence of the SAO has been approved and adopted by the RNM Assembly. |  |  | / |  |  | / |  |  | / |
| Deliverables in 2024: | - Approved draft amendment to the Constitution of the RNM for SAO regulation as a constitutional category to be submitted by the authorized proposer of the constitutional amendment to the Assembly of the RNM for adoption; - A new draft State Audit Law aims to strengthen the financial and operational independence of the SAO to be approved and submitted to the RNM Assembly for adoption; - Proposals for by-laws based on the improved legal framework |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  | TIMEFRAME |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  |  | PLANNED INPUTS |  |  |
|  |  |  | START qq/yy | END qq/yy |  |  |  |  |  |  | BUDGET |  | SOURCE |
| 1. Approval of constitutional changes to achieve constitutional independence of the SAO in accordance with the principles, standards and guidelines of INTOSAI |  |  | К1/2022 | К4/2027 |  |  |  | Authorized proposer of the constitutional amendment; Assembly of RNM |  |  | 7,000 |  | External funding NDI and others |
| 2. Approval of external audit legal framework aimed at strengthening financial and operational independence of SAO in line with INTOSAI principles, standards and guidelines |  |  | К1/2022 | К4/2024 |  |  |  | Ministry of Finance, Government of RNM and Assembly of RNM |  |  | 14,000 |  | External funding NDI and others |
| MEASURE 2: Strengthening the institutional capacity and human resource capacities of the SAO |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  | Target FY 2024 |  |  | Target FY 2025 |  |  | Target FY 2026 |  |  | Target FY 2027 |
| Implementation of SAO Development Strategy 2023-2027 SAO Annual report on performed audits and operations | Percentage of implementation of SAO Development 2023-2027 |  |  | Percentage of implementation of the activities determined in the Strategy for the Development of SAO 2023 - 2027 - 40% |  |  | Percentage of implementation of the activities determined in the Strategy for the Development of SAO 2023 - 2027 - -60% |  |  | Percentage of implementation of the activities determined in the Strategy for the Development of SAO 2023 - 2027 - -80% |  | Percentage of implementation of the Strategy for the Development of SAO 2023 - 2027- 100% |  |
| Audit scope of total public expenditures SAO Annual report on performed audits and operations | Percentage of audit scope of total public expenditures |  |  | ≥60% |  |  | ≥60.5% |  |  | ≥61% |  | ≥61.5% |  |
| Results from stakeholder surveys on the added value of the SAO | Perception of stakeholders' on SAO added value |  |  | Stakeholders' perception of the added value of SAO-81% |  |  | Stakeholders' perception of the added value of SAO-82% |  |  | Stakeholders' perception of the added value of SAO-83% |  | Stakeholders' perception of the added value of SAO-85% |  |
| Deliverables in 2024: | - Analysis with recommendations for improving the audit process on the Annual Account of the Budget of the Republic of North Macedonia; - New or improved methodological acts and tools on topics relevant to the responsible management and use of public funds for audits of sustainable development goals, audits of financial statements prepared on an accrual basis, audits of value for money (Value for Money), audits of LSGU, audit of public enterprises and state-owned companies, audit of financial statements of the Core budget etc. - Conducted performance audits in relevant areas of government policy and audits on certain topics of importance for the responsible management and use of public funds (audit of EU funds, audits of sustainable development goals, audit of financial statements prepared on an accrual basis, audit of values for money (Value for money), audits of LGUs, gender equality audit, audits in the areas determined in the National Development Strategy of the Republic of North Macedonia,, etc.); - Conducted training (study visits, conferences, seminars, workshops) according to SAO Annual plan for continuous profesional development for 2024; - Trainings, and workshops for strengthen cooperation with stakeholders and anticorruption bodies; - Using modern auditing tools, methodologies, techniques, and development of software tools for reclassification of financial statements/software tools for auditing financial statements prepared on an accrual basis; - Use of modern equipment and improved working conditions - Using visualization (infographics, video presentations, flyers) to present the results of the audit to the public. - New channels for communication with stakeholders (the Assembly, the Government, the Ministry of Finance, the Public Prosecutor's Office, the Ministry of Internal Affairs, the State Commission for the Prevention of Corruption, the entities subject to audit, the public); - Using digital tools to achieve efficient cooperation and communication with parliamentary bodies to support the work of the RNM Assembly; - Conducting peer review according to the International standards of INTOSAI; - New forms for monitoring and presenting the implementation of audit recommendations |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  | TIMEFRAME |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  |  | PLANNED INPUTS |  |  |
|  |  |  | START qq/yy | END qq/yy |  |  |  |  |  |  | BUDGET |  | SOURCE |
| 1. Implementation of adopted new and improved SAO strategic, planning and methodological acts of the SAO and adoption of new methodological acts |  |  | К1/2024 | К4/2027 | SAO |  |  |  |  |  | 100,000 |  | External funding WFD, NDI, USAID, UNDP, UnWomen and others |
| 2. Strengthen the capacity to conduct audits |  |  | К1/2024 | К4/2027 | SAO |  |  |  |  |  | 862,400 (156,000 financial gap+706,400 external funfing) |  | External funding WFD, NDI, USAID, UNDP, UnWomen and others |
| 3. Increasing the visibility of the SAO and communication with the stakeholders |  |  | К1/2024 | К4/2027 | SAO |  |  | Stakeholders (Assembly, Government, Ministry of Finance, Public Prosecutor's Office, Ministry of Interior, State Commission for Prevention of Corruption, audited entities, the public). |  |  | 200,000 |  | External funding WFD, NDI, USAID, UNDP, UnWomen and others |
|  |  |  |  |  |  |  |  |  |  |  | TOTAL: |  | EUR 1.183.400 |

| PILLAR VII: External Audit and Parliamentary Oversight |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PRIORITY 2: Parliamentary Oversight |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Priority outcomes | Priority indicators |  |  | Target FY 2024 |  |  |  | Target FY 2025 |  |  | Target FY 2026 |  |  |  | Target FY 2027 |
| Enhanced effects of audit. | Percentage of external audit recommendations for which corrective measures have been taken. |  |  | ≥72% |  |  |  | ≥74% |  |  | ≥76% |  |  |  | ≥78% |
| MEASURE 1: Establishing a mechanism for reviewing the audit reports and the measures taken following the recommendations given in the audit reports in the RNM Assembly |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: |  |  | Measure indicator: |  |  | Target FY 2024 |  |  | Target FY 2025 |  |  | Target FY 2026 |  |  | Target FY 2027 |
| Strengthening institutional mechanism for reviewing audit reports by the Assembly of RNM. |  |  | Number of audit reports reviewed by the Assembly. |  |  | Number of audit reports reviewed by the Assembly. ≥2 |  |  | Number of audit reports reviewed by the Assembly. ≥3 |  |  | Number of audit reports reviewed by the Assembly. ≥4 |  |  | Number of audit reports reviewed by the Assembly. ≥5 |
| Deliverables in 2024: |  | - Final procedures of the SAO for preparing and submitting audit reports and other documents to the RNM Assembly; - Proposal - procedures for manner of reviewing audit reports (from receipt of audit reports and other documents to adoption conclusions and monitoring implementation of audit recommendations) in the RNM Assembly; - Summary reports from the final audit reports for certain areas submitted to the RNM Assembly; - Education on the enacted acts |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  |  |  | TIMEFRAME |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  |  | PLANNED INPUTS |  |  |
|  |  |  |  |  | START qq/yy | END qq/yy |  |  |  |  |  |  | BUDGET |  | SOURCE |
| 1.Implementation of concluded Memorandum of Cooperation between the Assembly and the SAO. |  |  |  |  | К4/2022 | К4/2027 | SAO |  |  | RNM Assembly |  |  | / |  | / |
| 2.Preparation of final/proposal procedures in the SAO and the Assembly for submission and review of audit reports and other documents. |  |  |  |  | К2/2022 | К4/2027 | SAO |  |  | RNM Assembly |  |  | 9,200 |  | External financing NDI and others |
| 3.Reviewing of summary reports from final audit reports from certain areas by the Assembly. |  |  |  |  | К3/2022 | К4/2027 | SAO |  |  | RNM Assembly |  |  | 20,000 |  | External financing NDI, WFD and others |
| MEASURE 2: Strengthening the institutional capacities for reviewing audit reports in the Assembly of RNM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: |  |  | Measure indicator: |  |  | Target FY 2024 |  |  | Target FY 2025 |  |  | Target FY 2026 |  |  | Target FY 2027 |
| Strengthened institutional capacities for reviewing the audit reports in the Assembly of RNM. |  |  | Number of MPs trained on the role of the SAO. |  |  | Number of MPs trained on the role of the SAO – 10. |  |  | Number of MPs trained on the role of the SAO – 13. |  |  | Number of MPs trained on the role of the SAO – 16. |  | Number of MPs trained on the role of the SAO – 19. |  |
| Deliverables in 2024: |  | - A training plan for MPs in the Committee on Financing and Budget and other MPs who participate in the committees and employees of the RNM Assembly Service to facilitate the understanding of audit reports and preparation for discussion on audit reports; - Conducting trainings in accordance with the Training Plan for MPs and employees of the Service in order to understand the audit reports and to prepare for the debate on the audit reports (through study visits, workshops, case studies, debate simulations); - Activities to strengthen cooperation with the Committee on Financing and Budget, the Parliamentary Institute and the Parliamentary Budget Office of the Assembly of the RNM |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  |  |  | TIMEFRAME |  | RESPONSIBLE INSTITUTION |  |  | OTHER INSTITUTIONS INVOLVED |  |  | PLANNED INPUTS |  |  |
|  |  |  |  |  | START qq/yy | END qq/yy |  |  |  |  |  |  | BUDGET |  | SOURCE |
| 1. Preparation of a Training Plan for MPs and employees of the RNM Assembly Service in order to facilitate the understanding of the audit reports and preparation for a debate on the audit reports. |  |  |  |  | К4/2024 | К4/2027 | SAO |  |  | RNM Assembly |  |  | 2,200 |  | External financing NDI and others |
| 2. Conducting trainings in accordance with the Training Plan for the Members of Parliament and employees of the RNM Assembly Service in order to facilitate the understanding of the audit reports and preparation for the debate on the audit reports. |  |  |  |  | К4/2024 | К4/2027 | SAO |  |  | RNM Assembly |  |  | 28,000 |  | External financing NDI, WFD and others |
| 3. Implementation of activities for strengthening cooperation with Committee on Financing and Budget, Parliamentary Institute and the Parliamentary budget office of the RNM Assembly. |  |  |  |  | К2/2023 | К4/2027 | SAO |  |  | Committee on Financing and Budget, Parliamentary Institute and Parliamentary Budget Office of the Assembly of RNM |  |  | 24,000 |  | External financing NDI, WFD and others |
|  |  |  |  |  |  |  |  |  |  |  |  |  | TOTAL: |  | EUR 83,400 |

| PILLAR VIII: PFM at Local Level |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PRIORITY 1: Fiscal Decentralisation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Priority outcomes | Priority indicators | Target FY 2024 |  |  |  |  |  |  | Target FY 2025 |  |  |  |  |  |  | Target FY 2026 |  |  |  |  | Target FY 2027 |  |  |  |
| Improved fiscal capacity and increased municipal revenues | Percentage of increased municipal revenues compared to 2022 | 15% |  |  |  |  |  |  | 20% |  |  |  |  |  |  | 25% |  |  |  |  | 30% |  |  |  |
|  | Ratio of local revenues as % of GDP | 5,5% |  |  |  |  |  |  | 6% |  |  |  |  |  |  | 6,5% |  |  |  |  | 7% |  |  |  |
|  | Ratio of local revenues as percentage of total public revenues | 17% |  |  |  |  |  |  | 18% |  |  |  |  |  |  | 19% |  |  |  |  | 20% |  |  |  |
| MEASURE 1: Improving fiscal capacity and increasing municipal revenues |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  | Target FY 2024 |  |  |  |  | Target FY 2025 |  |  |  |  |  |  | Target FY 2026 |  |  |  | Target FY 2027 |  |  |  |
| Strengthening the fiscal capacity of the Municipalities through the adoption of a new Law on financing of LGU and by-laws, increasing the revenues of the municipalities through amendments to the legislation, adoption of new Decrees for block and earmarked grants for transferred competencies and determination of criteria for allocation of capital transfers | New law on financing of local self-government units |  |  |  | New law on financing of local self-government units |  |  |  |  | / |  |  |  |  |  |  | / |  |  |  | / |  |  |  |
|  | By-laws of the new Law on financing of local self-government units |  |  |  | 50% of by- laws |  |  |  |  | 50% of by- laws |  |  |  |  |  |  | / |  |  |  | / |  |  |  |
|  | Revised Property Tax law |  |  |  | / |  |  |  |  | / |  |  |  |  |  |  | Amended Property Tax Law/New By laws |  |  |  | continue |  |  |  |
|  | Revised Law on communal fees |  |  |  | / |  |  |  |  | / |  |  |  |  |  |  | Amended Law on Communal Fees |  |  |  | X |  |  |  |
|  | Prepared analysis of other laws regulating municipal own revenues |  |  |  | / |  |  |  |  | 1 |  |  |  |  |  |  | 1 |  |  |  | 1 |  |  |  |
|  | Number of revised decrees on block grants, earmarked grant and New Decree/s for distribution of capital grants |  |  |  | Two new decrees for block grants |  |  |  |  | New Decree on distribution of grant for firefighters and Two new decrees for block grants |  |  |  |  |  |  | One new decree for block and one Decree of capital grants |  |  |  | Two new decrees for capital grants |  |  |  |
| Deliverables in 2024: | New law on financing of local self-government units 50% of by- laws Report for amendments to the Property tax law Report with analysis for amendments to the Property tax law Two new decrees for block grants and new Decree on distribution of grant for firefighters |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  | TIMEFRAME |  |  |  | RESPONSIBLE INSTITUTION |  |  |  |  | OTHER INSTITUTIONS INVOLVED |  |  |  |  |  | PLANNED INPUTS |  |  |  |  |  |  |
|  |  |  | START qq/yy | END qq/yy |  |  |  |  |  |  |  |  |  |  |  |  |  | BUDGET |  |  |  |  |  | SOURCE |
| 1. Addoption of a New Law on Financing Local Government Units |  |  | Q1/24 | Q4/24 |  |  | Ministry of Finance |  |  |  |  | Municipalities |  |  |  |  |  | 20.000 |  |  |  |  |  | Donors |
| 2. Preparation of by-laws of the new Law on financing of local self-government units |  |  | Q3/24 | Q2/25 |  |  | Ministry of Finance |  |  |  |  | Municipalities |  |  |  |  |  | 5.000 |  |  |  |  |  | Donors |
| 3.Improving the legal regulation for local revenues |  |  | Q1/24 | Q4/27 |  |  | Ministry of Finance |  |  |  |  | Municipalities |  |  |  |  |  | 5.000 |  |  |  |  |  | USAID UNDP |
| 4. Revision of the criteria for distribution of block and earmarked grants and determination of criteria for allocation of capital grants |  |  | Q1/24 | Q4/27 |  |  | Ministry of Finance, Ministry of Education and Science, Ministry of Labor and Social Policy, Ministry of Culture, Ministry of Defense, Other competent ministries and institutions, where from capital grants are transferred |  |  |  |  | Municipalities |  |  |  |  |  | 3.000 |  |  |  |  |  | Donors |
| MEASURE 2: Regional and local development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  | Target FY 2024 |  |  |  |  | Target FY 2025 |  |  |  |  |  |  | Target FY 2026 |  |  |  |  | Target FY 2027 |  |  |
| The establishment of this agency will enable easier access to financial resources of the municipalities for the realization of investment projects. Simultaneously with the Municipal Development Index (MDI) which will offer valuable insights into the overall development of municipalities by providing a comprehensive assessment of key indicators, promoting sustainable and inclusive development of the municipality. | Established Agency for regional and local development |  |  |  | Report with legal and operational solutions for the establishment of the Agency |  |  |  |  | Established Agency for Regional and Local Development |  |  |  |  |  |  | monitoring the work of the agency |  |  |  |  |  | monitoring the work of the agency |  |
|  | Municipal development index |  |  |  | +5 new indicators |  |  |  |  | +5 new indicators |  |  |  |  |  |  | +5 new indicators |  |  |  |  |  | +5 new indicators |  |
| Deliverables in 2024: | - Report with legal and operational solutions for the establishment of the Agency - +5 new indicators |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  | TIMEFRAME |  |  |  | RESPONSIBLE INSTITUTION |  |  |  |  | OTHER INSTITUTIONS INVOLVED |  |  |  |  |  | PLANNED INPUTS |  |  |  |  |  |  |
|  |  |  | START qq/yy | END qq/yy |  |  |  |  |  |  |  |  |  |  |  |  |  | BUDGET |  |  |  |  |  | SOURCE |
| 1. Establishment of the Agency for Regional and Local Development and achieving balanced regional development |  |  | Q1/24 | Q4/27 |  |  | Ministry of Local Self -Government Ministry of Finance |  |  |  |  | Bureau for Regional Development, MoF, Cabinet of the DPM for Еconomic Аffairs, Ministry of Justice, Ministry of Political System аnd Community Relations, MISA |  |  |  |  |  | 5.000 |  |  |  |  |  | USAID Donors |
| 2. Determination of municipal development index |  |  | Q1/24 | Q4/27 |  |  | Ministry of Finance Ministry of Local Self -Government UNDP |  |  |  |  | Municipalities ZELS UNDP |  |  |  |  |  | 20.000 |  |  |  |  |  | UNDP |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | TOTAL: |  |  |  |  |  |  | EUR 58,000 |  |  |
| - PILLAR VIII: PFM at Local Level |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PRIORITY 2. Financial Discipline, Transparency and Accountability at the Local Level |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Priority outcomes | Priority indicators | Target FY 2024 |  |  |  |  |  |  | Target FY 2025 |  |  |  | Target FY 2026 |  |  |  |  |  |  | Target FY 2027 |  |  |  |  |
| Increased financial discipline | Percentage of reduction of the amount of due unpaid liabilities in the current year compared to 2022 | 10% |  |  |  |  |  |  | 20% |  |  |  | 30% |  |  |  |  |  |  | 40% |  |  |  |  |
|  | Reduction of the number of municipalities with blocked account in the current year compared to 2022 | 2 |  |  |  |  |  |  | 3 |  |  |  | 4 |  |  |  |  |  |  | 5 |  |  |  |  |
| Increased transparency and accountability of municipalities. | Percentage of municipalities out of the total number of municipalities (81) that have published financial documents (annual, semi-annual and quarterly reports) on their websites. | 75% |  |  |  |  |  |  | 80% |  |  |  | 90% |  |  |  |  |  |  | 100% |  |  |  |  |
| MEASURE 1: Increasing the financial discipline |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  | Target FY 2024 |  |  |  |  | Target FY 2025 |  |  |  | Target FY 2026 |  |  |  |  | Target FY 2027 |  |  |  |  |  |
| Realistic planning of revenues and expenditures of municipalities, rationalization of operations and reduction of unnecessary expenditures, regular servicing of liabilities, greater financial discipline, procedures for declaring financial instability, issuance of financing instruments to overcome the financial instability of municipalities and analysis of existing liabilities of municipalities and public enterprises. | Number of trained employees in the LGU |  |  |  | 81 |  |  |  |  | 81 |  |  |  | 81 |  |  |  |  | 81 |  |  |  |  |  |
|  | Number of additional employments in the Unit for LGU Budgets |  |  |  | 2 |  |  |  |  | 2 |  |  |  | 1 |  |  |  |  | 1 |  |  |  |  |  |
|  | Percentage of realized revenues in relation to the planned ones during the current year |  |  |  | 86% |  |  |  |  | 89% |  |  |  | 90% |  |  |  |  | 92% |  |  |  |  |  |
|  | Percentage of share of capital expenditures in relation to the total expenditures in the current year |  |  |  | 28% |  |  |  |  | 30% |  |  |  | 33% |  |  |  |  | 35% |  |  |  |  |  |
|  | New Law on unpaid obligations of the municipalities |  |  |  | New Law on unpaid obligations of the municipalities |  |  |  |  | / |  |  |  | / |  |  |  |  | / |  |  |  |  |  |
|  | By-laws of a New Law on unpaid obligations of the municipalities |  |  |  | 50% new by-laws |  |  |  |  | 50% new by-laws |  |  |  | / |  |  |  |  | / |  |  |  |  |  |
|  | Internal procedures for declaring financial instability |  |  |  | Internal procedures for declaring financial instability |  |  |  |  | / |  |  |  | / |  |  |  |  | / |  |  |  |  |  |
| Deliverables in 2024: | - 81 trained employees in the LGU - 2 additional employments in the Unit for LGU Budgets - 86% realized revenues in relation to the planned ones during the current year - 28% share of capital expenditures in relation to the total expenditures in the current year - New Law on unpaid obligations of the municipalities - 50% by-laws of a New Law on unpaid obligations of the municipalities - Internal procedures for declaring financial instability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  | TIMEFRAME |  |  |  | RESPONSIBLE INSTITUTION |  |  |  | OTHER INSTITUTIONS INVOLVED |  |  |  | PLANNED INPUTS |  |  |  |  |  |  |  |  |  |
|  |  |  | START qq/yy | END qq/yy |  |  |  |  |  |  |  |  |  |  | BUDGET |  |  |  |  |  |  | SOURCE |  |  |
| 1. Trainings for strengthening the capacities of the employees in the municipalities for realistic planning of the revenues and expenses of the municipalities |  |  | Q1/24 | Q1/27 |  |  | Ministry of Finance |  |  |  | Municipalities |  |  |  | 8.000 |  |  |  |  |  |  | National Budget |  |  |
| 2. Strengthening the capacity of employees in the Unit of budget of the local self-government unit |  |  | Q1/24 | Q1/27 |  |  | Ministry of Finance |  |  |  |  |  |  |  | 18.600 |  |  |  |  |  |  | National Budget |  |  |
| 3. Decreasing current expenses and increasing capital expenses in the structure of total expenses by establishing performance indicators |  |  | Q1/24 | Q1/27 |  |  | Ministry of Finance |  |  |  | Municipalities |  |  |  | / |  |  |  |  |  |  | National Budget |  |  |
| 4. New Law on unpaid obligations of the municipalities |  |  | Q1/24 | Q2/25 |  |  | Ministry of Finance |  |  |  | Municipalities USAID ZELS MLS |  |  |  | 20.000 |  |  |  |  |  |  | National Budget |  |  |
| MEASURE 2: Increasing the transparency and accountability throughout the operations of the municipalities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure objective: | Measure indicator: |  |  |  | Target FY 2024 |  |  |  |  | Target FY 2025 |  |  |  | Target FY 2026 |  |  |  |  | Target FY 2027 |  |  |  |  |  |
| Increased control by the state, in particular by the Department for Public Sector Financial Inspection in terms of compliance with the provisions of the Law on Reporting and Recording of Liabilities, the Law on Financial Discipline and the Law on Financing Local Government Units, increasing the transparency of municipalities by publishing financial statements in a transparent and understandable manner, as well as greater accountability for the use of budget funds | Number of oversight conducted by the all ministries that transfer funds from the Budget of RNM |  |  |  |  |  |  |  |  | 1 |  |  |  | 3 |  |  |  |  | 5 |  |  |  |  |  |
|  | Number of municipalities that regularly publish financial reports |  |  |  | 65 |  |  |  |  | 70 |  |  |  | 75 |  |  |  |  | 81 |  |  |  |  |  |
|  | Number of reports on the financial operations of the municipalities published on the web page of the Ministry of Finance |  |  |  | 6 |  |  |  |  | 7 |  |  |  | 8 |  |  |  |  | 9 |  |  |  |  |  |
|  | Number of reports with data on due and unpaid liabilities from the ESPEO system of 81 the municipalities published on the web page of the Ministry of Finance |  |  |  | 4 |  |  |  |  | 4 |  |  |  | 4 |  |  |  |  | 4 |  |  |  |  |  |
| Deliverables in 2024: | - 65 municipalities regularly published financial reports - 6 reports on the financial operations of the municipalities published on the web page of the Ministry of Finance - 4 reports with data on due and unpaid liabilities from the ESPEO system of 81 the municipalities published on the web page of the Ministry of Finance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY |  |  | TIMEFRAME |  |  |  | RESPONSIBLE INSTITUTION |  |  |  | OTHER INSTITUTIONS INVOLVED |  |  |  | PLANNED INPUTS |  |  |  |  |  |  |  |  |  |
|  |  |  | START qq/yy | END qq/yy |  |  |  |  |  |  |  |  |  |  | BUDGET |  |  |  |  |  |  | SOURCE |  |  |
| 1 Increasing the oversight of municipalities for the purposeful spending of earmarked, block and capital grants by the competent ministries and institutions |  |  | Q2/25 | Q4/27 |  |  | Ministry of Finance and all ministries who transfer funds from the Budget of RNM |  |  |  | Municipalities |  |  |  | / |  |  |  |  |  |  | / |  |  |
| 2. Monitoring the transparency of the municipalities in order to timely inform the general public |  |  | Q1/24 | Q4/27 |  |  | Ministry of Finance |  |  |  | Municipalities |  |  |  | / |  |  |  |  |  |  | / |  |  |
| 3.Increasing the transparency of the Ministry of Finance for the financial operations of the municipalities |  |  | Q1/24 | Q4/27 |  |  | Ministry of Finance |  |  |  | Municipalities |  |  |  | / |  |  |  |  |  |  | / |  |  |
| 4.Participation of citizens in policy decision making and monitoring results |  |  | Q1/24 | Q4/27 |  |  | Ministry of Finance |  |  |  | Municipalities |  |  |  | / |  |  |  |  |  |  | / |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | TOTAL: |  |  |  |  |  |  | EUR 46,600 |  |  |

| Pillars | Priority | Budget |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | National budget | Donor funds | Financial gap | Total |
|  |  | in EUR | in EUR | in EUR | in EUR |
| I Economic Analysis, Macroeconomic and Fiscal Framework | 1.Revenue forecasting and reporting | 0 | 200,000 | 0 | 200,000 |
|  | 2.Economic analysis and Macroeconomic forecasting | 0 | 340,000 | 0 | 340,000 |
|  | 3.Strengthening Debt Management | 9,500 | 0 | 0 | 9,500 |
| II Revenue Mobilization | 1.Tax and Customs Policy | 0 | 250,000 | 0 | 250,000 |
|  | 2.Tax Administration | 2,577,000 | 0 | 0 | 2,577,000 |
|  | 3.Customs | 0 | 6,000,000 | 0 | 6,000,000 |
| III Planning and Budget | 1.Budget Planning | 0 | 654,000 | 0 | 654,000 |
|  | 2.Strengthened Public Investment Management | 64,000 | 160,000 | 0 | 224,000 |
|  | 3. Strengthen the accounting of budgets and budget users | 0 | 10,000 | 0 | 10,000 |
| IV Public procurement | 1.Public Procurement Policy | 84,000 | 0 | 0 | 84,000 |
|  | 2. Public Private Partnership and Concessions on goods of general interest | 48,000 | 0 | 511,000 | 559,000 |
| V Horizontal public finance management processes | 1. Implementation of an Integrated Financial Management Information System (IFMIS) | 0 | 0 | 0 | 0 |
|  | 2. P Public Finance Academy (Learning organisation) | 0 | 30,000 | 0 | 30,000 |
| VI Public Internal Financial Control | 1.Financial Management and Control | 10,000 | 32,000 | 0 | 42,000 |
|  | 2.Internal Audit | 32,000 | 20,000 | 0 | 52,000 |
| VII External audit and parliamentary oversight | 1.External audit | 0 | 1.027,400 | 156,000 | 1,183,400 |
|  | 2.Parliamentary Oversight | 0 | 83,400 | 0 | 83,400 |
| VIII PFM at Local Level | 1.Fiscal Decentralisation | 0 | 58,000 | 0 | 58,000 |
|  | 2.Financial Discipline, Tranparency and Accountability at the Local Level | 46.600 |  |  | 46,600 |
| Total |  | 2,871,500 | 8,864,800 | 667,000 | 12,402,900 |

The ongoing IFMIS procurement process follows established procedures, making it impractical to provide an exact budget amount at this stage.